## Sheet1
Status | (Multiple Items)
Row Labels | Count of Known Projects, Tasks, Activities, Needs
Jim | 1
Troy | 1
Joe | 1
Jennifer | 1
Kenny | 1
Amy | 1
Rebekah | 1
Malissa | 2
Suzanne | 2
MSC Lead | 2
Tracy | 2
Tom | 2
TBD | 2
Pam | 3
Cara | 3
Jo | 4
Jennie | 5
Amelea | 5
(blank) | 5
Grand Total | 44

## ProjectTaskDetails
Known Projects, Tasks, Activities, Needs | Phase | Lead Work Group | Lead Staff | Additional staff | Resources available | Priority rank from Lead | Known Milestones | Milestone Dates | Status | Intended Impact | Framework | Notes
HB633 Study - Planning, Prep, Communication | Planning | Admin | Jennie | Commissioners, Managers and leads | Yes | 1 | 1. Review and provide comment on study scope, | 2019-08-16 | Complete | Study will result in legislation that is passed by the 2021 Legislature that provides more diverse and stable funding for the State Library | Funding
[7 empty] | 2. Subcommittee Meeting | 2019-09-18
[7 empty] | 3. Develop data and reporting based on Committee requests | On-going through September2020
[7 empty] | 4. Identify and recruit advocates | On-going through September2020
Study administration of the Montana Natural Heritage Program | In Progress | Admin | Jennie | Malissa, Evan, Bryce, Commission | Yes | 2 | 1. Identify and organize study questions and resources to address questions | 2019-09-30 | On Schedule | Staff will have more confidence that the administrative model of the MTNHP is appropriate and adequate; if changes are made they should improve work efficieny and financial stability for MTNHP and MSL | Funding
[7 empty] | 2. Communicate regularly with stakeholders (Commission, staff, UM , Budget Office) | On-going through December 2020
[7 empty] | 3. Research study questions to determine whether or not adminstrative change is warranted | 2019-12-14
[7 empty] | 4. Make a final recommendation to the Commission regarding administrative changes | 2019-12-14
Org Flattening | In Progress | Admin | Jennie |  |  | 3 | 1. Maintain ongoing communication with staff | Ongoing
Website Updates - Reorganization/rewrite, Web Accessibility | In Progress | Admin | Tom | Kenny, Stanley | Vendor Needed | 2 |  |  | Will begin after VDI/Win 10 |  | Information Infrastructure
Virtual desktop implementation/Windows 10 | In Progress | Admin | Tom | Joe, Stanley | Yes | 1 |  | November 2019 Completion | Ongoing |  | Information Infrastructure
Performance management - Initiate use of state performance management system | Planning | Admin | Jennie | [7 empty] | Funding
Pay equity and pay policy improvement | Planning | Admin | Malissa | Jennie, Evan
Intranet improvement | Planning | Admin | Malissa | [7 empty] | Information Infrastructure
LiDAR - Implement Statewide Plan | In Progress | Info Management | Troy | GIS Analyst and Tech for data management/processing, GIS Coordinator and Data Coordinator for outreach, Info products and IT for web services | Yes; funding for storage? | 1 | 1. Develop posters/postcards one-pagers about State Lidar Plan; | 1. 20-Sept-2019 (hard, then ongoing); |  | Statewide high-resolution elevation data by end of 2023, MSL becomes the repository for lidar data | Partnerships | User Services
[7 empty] | 2. Apply for USGS 3DEP BAA in Fall 2019 for lidar acquisitions Spring/Fall 2020; | 2. 1-Nov-2019 (hard);
[7 empty] | 3. Collect and store lidar data for all known acquisitions; | 3. 1-Feb-2020 (soft);
[7 empty] | 4. Develop prototype lidar data delivery system. | 4. 30-June-2020 (soft).
MARC record project. | Planning | Info Management | Jim | Jemma, Kenny | Contractor needed |  | Scope project. Develop contract. | 11/1/2019 (tentative) | Planning | Improved, cleaner access to print and digitized state publications. Supports growth of digital depositories among Montana libraries.
Digital Public Library of America - Complete and evaluate ebook pilot | In Progress | Info Products | Jennie | Cara, Kenny, Rebekah | [6 empty] | Information Infrastructure
Productivity Tools - Project Management - identify tools, educate, and implement consistent practice | In Progress | Info Products | Evan | Joe, Tom, Jennifer, Erin, Jemma | [6 empty] | Funding
MSC Cloud-based ILS reporting migration and data standardization (Phase 1) | In Progress | Info Products | MSC Lead | Amy, Jemma, Rebekah, Keiley | Yes | 2 | 1. Audit five configuration areas and reports | Dates dependent on lead assignment |  | We are making it possible to respond to user demand for more modern software. A cloud-based solution will be a more secure platform and increase support efficiences. Our vendor has made it clear that this is the direction they are moving, and to avoid being stuck on a legacy product, we are laying the foundation for a smooth transition. This is a first phase in laying the foundation for a cloud-based ILS in two to three years. | Information Infrastructure | See project tracker online: https://app.asana.com/0/1126479711917387/1126479711917387
2. Establish standards and documentation
3. Migrate reports to BLUEcloud
4. BLUEcloud Central configuration with vendor
5. Develop and deliver training materials.
MSC security audit | Planning | Info Products | MSC Lead | Amy, Jemma, Rebekah, Tom, Jennie | Startup funding in place for VPN; need to assess time | 1 | 1. Collect technology network information from member libraries. | Dates dependent on lead assignment |  | This project will bring us into compliance with state law for securing data in transit. | Information Infrastructure | See project tracker online: https://app.asana.com/0/1126479711917387/1126479711917387
2. Complete ITSD security audit form...Last step: Deploy VPN
Review of ArcGIS Server Environment Needs - Enterprise, Portal, EMCS Dev, etc. | In Progress | Info Products | Joe | [7 empty] | Information Infrastructure | IT
Cadastral Refresh - Interface updates and roll-out/promotion | In Progress | Info Products | Kenny | [7 empty] | Information Infrastructure | User Services
MSC mobile friendly ILS | In Progress | Info Products | Rebekah | Keiley | Member funding for app | 3 | 1. Test server upgrade to enable responsive design | Sept-Oct - test server upgrade; Nov-Dec - test server debugging and code revisions; |  | With 1/3 of Montana Shared Catalog users accessing the catalog via a mobile device, working to develop a mobile friendly ILS will increase access and improve user experience. | Information Infrastructure | See project tracker online: https://app.asana.com/0/1126479711917387/1126479711917387
2. Complete debugging, js widget and CSS revisions
[7 empty] | 3. Mobile app put to membership vote | Oct - mobile app member vote;
[7 empty] | 4. Mobile profile testing | Jan-Feb - Mobile profile testing;
[7 empty] | 5. Update production | Mar - production update;
[7 empty] | 6. Document changes in knowledge base | Apr - documentation
Standardize MSC user sharing groups | Planning | Info Products | Amy | MSC Lead, Jemma, Rebekah, Cara, Keiley | Yes; possible pilot funding | 4 | 1. Establish a Sharing Group Committee with representation from all existing sharing groups and interested silo libraries. | Dates dependent on lead assignment; Oct - solicit for committee volunteers; Jan - committee meeting; May - report on findings |  | Increased standardization will position the MSC for a more competitive RFI/RFP process. A more standardized system is more sustainable and scalable and will increase support efficiences. It will make it easier to train member libraries because we will have uniform procedures based on uniform config. It will increase capacity for the courier, ultimately getting more books into the hands of Montanans and creating more equitable access. | Information Infrastructure | See project tracker online: https://app.asana.com/0/1126479711917387/1126479711917387
Census 2020 | In Progress | User Services | Jennie | Jo, Tracy | yes | 2 | 1. Printing of posters, etc; | 1. Mid-September |  | Ensure an accurate Census count in Montana | Partnerships | Info Mgmt/Info Infra?
[7 empty] | 2. Training | 2. End of September
[7 empty] | 3. Census Day | 3. April 1, 2020
Public Library Standards revision | In Progress | User Services | Tracy | Jennie, Cara | yes | 4 | 1. PLSTF Meeting | 1. September 13, 2019 |  | Ensure that Montanans have access to library services sufficient unto their needs | Information Infrastructure | Funding?
[7 empty] | 2. 1st Draft of standards | 2. October 2019
[7 empty] | 3. Review and final draft of standards | 3. December 2020
[7 empty] | 4. Public comment | 4. January/February 2020
[7 empty] | 5. Administrative Rules process | 5. Spring 2020
[7 empty] | 6. Adoption of new standards | 6. June 2020
Statewide data driven model/regional RIPL follow-up | In Progress | User Services | Jo | Tracy | yes | 3 | 1. RIPL Training 2. Follow-up meeting with Colorado State Library 3. Implementation of follow-up plan created with Colorado State Library | 1. October 10, 2019 2. October 11, 2019 |  | Attendees use data to plan and evaluate services. Attendees are better able to communicate the value of library services. | Information Infrastructure | Also could work towards secure sufficient funding
Ready 2 Read Rendezvous | In Progress | User Services | Amelea | Pam, Jo | yes | 1 | 1. R2R training offered | 1. September 2019 4. Summer 2020 |  | Librarians incorporate early literacy/early learning skill building in children's programming to assist Montana's youngest residents succeed later in life. | Information Infrastructure
[7 empty] | 2. Follow-up with attendees | 2. Fall/Winter 2019/2020
[7 empty] | 3. Application of what was learned | 3. Spring 2020
[7 empty] | 4. Evaluation of project | 3. Winter/Spring 2020
Transition to Bibliostat | In Progress | User Services | Pam | Tracy | yes | 1 | 1. Data is migrated to Bibliostat | 1. August/September 2019 |  | Create staff efficiences and provide librarians with access to statistics in order to evaluate their services and communicate their value. | Information Infrastructure
[7 empty] | 2. Statistics forms and historical reports are created | 2. September 2019
[7 empty] | 3. Product go live for libraries | 3. September 2019
[7 empty] | 4. Librarians submit statistics and can use historical reports | 4. Fall 2019
[7 empty] | 5. Statistics are successfully uploaded to IMLS | 5. Winter 2020
Implement strategic plan pathway | In Progress | User Services | Jo | Tracy, Suzanne, Pam | yes | 5 | 1. Update certification manual with Commission adopted changes | 1. Late fall 2019 |  | Librarians have a certification pathway that assists them in achieving the library's strategic goals | Information Infrastructure
[7 empty] | 2. Webinar for librarians about new pathway | 2. Winter 2020
[7 empty] | 3. Assistance for librarians who follow the pathway | 3. Winter/Spring 2020
Director's Institute | In Progress | User Services | Jo | Tracy, Pam, Suzanne, Cara | yes | 2 | 1. Contract with facilitator is completed | 1. Fall 2019 |  | We build a cohort of collaborative leaders who trust each other, develop innovative ideas for libraries, are resilient, and able to have challenging conversations about barriers and scaling the project/program as needed. | Information Infrastructure | Foster partnerships
[7 empty] | 2. Planning for workshop is completed | 2. Fall/winter 2019
[7 empty] | 3. Institute is offered | 3. Early summer 2020
[7 empty] | 4. Follow-up with attendees is completed | 4. Summer/Fall 2020
YALSA Training | In Progress | User Services | Amelea | Cody Allen, Heather Dickerson | yes | 3 | 1. Cody and Heather's attendance at YALSA train the trainer event | 1. Fall 2019 |  | Librarians who serve young adults are empowered to provide relevant programming for their community members. | Information Infrastructure
[7 empty] | 2. Offering of trainings for librarians | 2. Spring 2020
CIT Training | In Progress | User Services | Amelea | Pam, Suzanne, Tracy | yes | 3 | 1. Trainings are complete | 1. Fall 2019/Spring 2020 |  | Librarians have skills to address patrons struggling with a crises. | Fostering Partnerships | Information Infrastructure
Volunteer program enhancements and administration | In Progress | User Services | TBD | [7 empty] | Partnerships
Grant management tool implementation | In Progress | User Services | Erin | John | [6 empty] | Partnerships
Adaptive technologies implementation | In Progress | User Services | TBD | [7 empty] | Information Infrastructure
Economic development - Implement and evaluate contract with economic development liaison | Planning | User Services | Amelea | Tracy, Jim, Erin, Jessica | yes | 2 | 1. Creation of limited solicitation | 1. Winter 2019 2. Winter 2019 3. Spring 2020 4. Summer 2020 |  | Montanans have the skills they need to obtain jobs or open small businesses. Local economic development officials are aware of the value of libraries in economic development work. | Information Infrastructure
[7 empty] | 2. Successful selection of vendor | 2. Winter 2019
[7 empty] | 3. Execution of contract | 3. Spring 2020
[7 empty] | 4. Deliverables that libraries can use | 4. Summer 2020
MTLibrary2Go - Conduct RFI/RFP | Planning | User Services | Cara |  | Yes |  | 1. RFI release by | 1. Mid-September; |  |  | Information Infrastructure
[7 empty] | 2. RFI scoring | 2. Late October;
[7 empty] | 3. RFP release | 3. Late November;
[7 empty] | 4. RFP scoring | 4. Late January;
[7 empty] | 5. New contract and budget | 5. June 30, 2020
OCLC (including MMP)- Conduct RFI/RFP | Planning | User Services | Cara | Chuck, Jennifer, Rebekah | Yes |  | 1. RFI release by | 1. Mid-September; |  |  | Information Infrastructure
[7 empty] | 2. RFI scoring | 2. Late October;
[7 empty] | 3. RFP release | 3. Late November;
[7 empty] | 4. RFP scoring | 4. Late January;
[7 empty] | 5. New contract and budget | 5. June 30, 2020
Realtime Network - create and grow Montana Network | Planning | User Services | Erin | [7 empty] | Partnerships | Info Infra?
Gigabit toolkit follow-up planning | Planning | User Services | Suzanne | Tracy, Jennie | maybe | 1 | 1. Analysis of data | 1. Fall 2019 |  | Every Montanan has access to high speed Internet. | Information Infrastructure
[7 empty] | 2. Tell library story about data | 2. Fall 2019
[7 empty] | 3. Action plan on addressing deficiencies with hardware and Internet speeds | 3. Winter 2020
[7 empty] | 4. Obtain resources for addressing deficiencie | TBD
[7 empty] | 5. Assist libraries with addressing deficiencies. | TBD
Cost share formula analysis | Planning | User Services | Cara | TBD |  |  | TBD |  |  |  | Information Infrastructure
GeoEnabled Elections | Planning | User Services | Erin | [7 empty] | Partnerships
MMP Collections - unrepresented counties and under-represented counties | In Progress | User Services | Jennifer |  | Yes |  | Collection from remaing 15 counties , improved collections from counties with only yearbooks | 2020-06-01 |  |  | Partnerships
Civic or civil engagement work | Planning | User Services | Amelea | Tracy, library staff |  | 2 | 1. Meeting of NAC sub-group and staff to identify a path | 1. November 2019
[7 empty] | 2. Create an action plan for implementing the path | 2. Winter 2020
[7 empty] | 3. Deliverables from the plan are created | 3. Spring 2020
[7 empty] | 4. Libraries use the deliverables | 4. Spring/Summer 2020
Public Library Board Member Development | Planning | User Services | Pam | Suzanne, Tracy | yes | 2 | 1. Increase number of trustees in MLA trustee interest group | 1. Fall 2019 |  | Board members are enaged and active members in the library community in order to improve library services. | Information Infrastructure | Foster partnerships
[7 empty] | 2. Increase enagement of the group | 2. Fall 2019
[7 empty] | 3. Offer trustee workshop | 3. Spring 2020
[7 empty] | 4. Follow-up with attendees to see if learning was applied | 4. Spring/early summer 2020
Update website for librarians and board members | Planning | User Services | Pam | Tracy, Suzanne, Jo, Amelea | yes | 1 | 1. Resources are updated | 1. Winter 2019 |  | Librarians and board members can find the resources they need to answer their questions. | Information Infrastructure
[7 empty] | 2. Website is made as user friendly as possible within existing parameters | 2. Winter 2019
[7 empty] | 3. End user feedback is obtained and acted upon if changes are needed | 3. Spring 2020
Foundations of librarianship course | Planning | User Services | Jo | Pam | yes | 3 | 1. Creation of modules for librarian course | 1. Winter 2019 |  | Librarians have the foundational knowledge needed to successfully run a library | Information Infrastructure
Virtual reality programming in libraries | Planning | User Services | Suzanne | Amelea | yes | 3 | 1. Research on implementation of VR in libraries | 1. Fall/winter 2019 |  | Montanans have access to virtual reality programs to learn, connect, and play. | Information Infrastructure
[7 empty] | 2. Create action plan for program | 2. Winter 2019
[7 empty] | 3. Offer session at OFFLINE | 3. February 2020
[7 empty] | 4. Deploy VR sets to Montana libraries | 4. Spring 2020
Increase financial and community support for libraries | Planning | User Services | Tracy | Jennie | yes | 2 | 1. Finalize the audience and plan for achieving this outcome | 1. Fall 2019 |  | Libraries have the community and financial support that allows them to offer services that help Montanans learn, make decisions, connect, and play.
[7 empty] | 2. Present a workshop for the audience | 2. Spring 2020
[7 empty] | 3. Follow-up with attendees | 3. Spring 2020
[7 empty] | 4. Evaluate progress and use to create the next plan and set of milestones | 4. Late spring/early summer 2020
Advisory Groups - improve engagement | Pre-planning | Admin
Agency Data & Records Management Strategy - including data sharing agreements | Pre-planning | Admin
Community Data Hub - What does this look like? What might we do with the hubs? | Pre-planning | Admin
Duplication on Demand for Talking Books | Pre-planning | Admin | [8 empty] | Partnerships
Information Infrastructure - Definition and gap analysis | Pre-planning | Admin | [8 empty] | Information Infrastructure
Outreach opportunities | Pre-planning | Admin | [8 empty] | Information Infrastructure
Partnerships - Define levels of engagement and ID partners; community charting; understanding partner needs | Pre-planning | Admin | Jennie | Commission, Jo, all staff | Yes | [5 empty] | Information Infrastructure
Reporting - Identify and improve strategies for agencywide reporting | Pre-planning | Admin | [8 empty] | Information Infrastructure
Request Management - Integrated process and tool(s); internal and external requests | Pre-planning | Admin | [8 empty] | Partnerships
Consistent public comment tool and process | Conceptual | Admin | [8 empty] | Partnerships
Productivity Tools - Password managers | Conceptual | Admin | [8 empty] | Funding
Productivity Tools - Tools updates and training | Conceptual | Admin | [8 empty] | Funding
Cross-training | Conceptual | Admin | [8 empty] | Information Infrastructure
Audit MSL web applications and prioritize updates | Pre-planning | Info Products | Kenny | Stanley, Chuck, Bob, Tom, Joe | [6 empty] | Information Infrastructure
Information Infrastructure
Information Infrastructure

## Project Tasks
Known Projects, Tasks, Activities, Needs | Phase | Lead Work Group | Lead Staff | Priority rank from Lead | Additional staff | Resources available | Status | Intended Impact | Framework | Notes
HB633 Study - Planning, Prep, Communication | Planning | Admin | Jennie | 1 | Commissioners, Managers and leads | Yes | Complete | Study will result in legislation that is passed by the 2021 Legislature that provides more diverse and stable funding for the State Library | Funding
Study administration of the Montana Natural Heritage Program | In Progress | Admin | Jennie | 2 | Malissa, Evan, Bryce, Commission | Yes | On Schedule | Staff will have more confidence that the administrative model of the MTNHP is appropriate and adequate; if changes are made they should improve work efficieny and financial stability for MTNHP and MSL | Funding
Org Flattening | In Progress | Admin | Jennie | 3
Website Updates - Reorganization/rewrite, Web Accessibility | In Progress | Admin | Tom | 2 | Kenny, Stanley | Vendor Needed | Will begin after VDI/Win 10 |  | Information Infrastructure
Virtual desktop implementation/Windows 10 | In Progress | Admin | Tom | 1 | Joe, Stanley | Yes | Ongoing |  | Information Infrastructure
Performance management - Initiate use of state performance management system | Planning | Admin | Jennie | 4 | Malissa, Evan, Leads, all staff | TBD | Awaiting action from DOA | Staff and managers will have a dynamic performance management system to track staff progress on work objectives and overal performance; staff have confidence that they are performing their jobs satisfactorily. | Funding
Pay equity and pay policy improvement | Planning | Admin | Malissa | 1 | Jennie, Evan | TBD
Intranet improvement | Planning | Admin | Malissa | 2 | John | Yes |  |  | Information Infrastructure
LiDAR - Implement Statewide Plan | In Progress | Info Management | Troy | 1 | GIS Analyst and Tech for data management/processing, GIS Coordinator and Data Coordinator for outreach, Info products and IT for web services | Yes; funding for storage? |  | Statewide high-resolution elevation data by end of 2023, MSL becomes the repository for lidar data | Partnerships | User Services
MARC record project. | Planning | Info Management | Jim |  | Jemma, Kenny | Contractor needed | Planning | Improved, cleaner access to print and digitized state publications. Supports growth of digital depositories among Montana libraries.
Digital Public Library of America - Complete and evaluate ebook pilot | In Progress | Info Products | Jennie |  | Cara, Kenny, Rebekah |  |  |  | Information Infrastructure
Productivity Tools - Project Management - identify tools, educate, and implement consistent practice | In Progress | Info Products | Evan |  | Joe, Tom, Jennifer, Erin, Jemma |  |  |  | Funding
MSC Cloud-based ILS reporting migration and data standardization (Phase 1) | In Progress | Info Products | MSC Lead | 2 | Amy, Jemma, Rebekah, Keiley | Yes |  | We are making it possible to respond to user demand for more modern software. A cloud-based solution will be a more secure platform and increase support efficiences. Our vendor has made it clear that this is the direction they are moving, and to avoid being stuck on a legacy product, we are laying the foundation for a smooth transition. This is a first phase in laying the foundation for a cloud-based ILS in two to three years. | Information Infrastructure | See project tracker online: https://app.asana.com/0/1126479711917387/1126479711917387
MSC security audit | Planning | Info Products | MSC Lead | 1 | Amy, Jemma, Rebekah, Tom, Jennie | Startup funding in place for VPN; need to assess time |  | This project will bring us into compliance with state law for securing data in transit. | Information Infrastructure | See project tracker online: https://app.asana.com/0/1126479711917387/1126479711917387
Review of ArcGIS Server Environment Needs - Enterprise, Portal, EMCS Dev, etc. | In Progress | Info Products | Joe | [5 empty] | Information Infrastructure | IT
Cadastral Refresh - Interface updates and roll-out/promotion | In Progress | Info Products | Kenny | [5 empty] | Information Infrastructure | User Services
MSC mobile friendly ILS | In Progress | Info Products | Rebekah | 3 | Keiley | Member funding for app |  | With 1/3 of Montana Shared Catalog users accessing the catalog via a mobile device, working to develop a mobile friendly ILS will increase access and improve user experience. | Information Infrastructure | See project tracker online: https://app.asana.com/0/1126479711917387/1126479711917387
Standardize MSC user sharing groups | Planning | Info Products | Amy | 4 | MSC Lead, Jemma, Rebekah, Cara, Keiley | Yes; possible pilot funding |  | Increased standardization will position the MSC for a more competitive RFI/RFP process. A more standardized system is more sustainable and scalable and will increase support efficiences. It will make it easier to train member libraries because we will have uniform procedures based on uniform config. It will increase capacity for the courier, ultimately getting more books into the hands of Montanans and creating more equitable access. | Information Infrastructure | See project tracker online: https://app.asana.com/0/1126479711917387/1126479711917387
Census 2020 | In Progress | User Services | Jennie | 2 | Jo, Tracy | yes |  | Ensure an accurate Census count in Montana | Partnerships | Info Mgmt/Info Infra?
Public Library Standards revision | In Progress | User Services | Tracy | 4 | Jennie, Cara | yes |  | Ensure that Montanans have access to library services sufficient unto their needs | Information Infrastructure | Funding?
Statewide data driven model/regional RIPL follow-up | In Progress | User Services | Jo | 3 | Tracy | yes |  | Attendees use data to plan and evaluate services. Attendees are better able to communicate the value of library services. | Information Infrastructure | Also could work towards secure sufficient funding
Ready 2 Read Rendezvous | In Progress | User Services | Amelea | 1 | Pam, Jo | yes |  | Librarians incorporate early literacy/early learning skill building in children's programming to assist Montana's youngest residents succeed later in life. | Information Infrastructure
Transition to Bibliostat | In Progress | User Services | Pam | 1 | Tracy | yes |  | Create staff efficiences and provide librarians with access to statistics in order to evaluate their services and communicate their value. | Information Infrastructure
Implement strategic plan pathway | In Progress | User Services | Jo | 5 | Tracy, Suzanne, Pam | yes |  | Librarians have a certification pathway that assists them in achieving the library's strategic goals | Information Infrastructure
Director's Institute | In Progress | User Services | Jo | 2 | Tracy, Pam, Suzanne, Cara | yes |  | We build a cohort of collaborative leaders who trust each other, develop innovative ideas for libraries, are resilient, and able to have challenging conversations about barriers and scaling the project/program as needed. | Information Infrastructure | Foster partnerships
YALSA Training | In Progress | User Services | Amelea | 3 | Cody Allen, Heather Dickerson | yes |  | Librarians who serve young adults are empowered to provide relevant programming for their community members. | Information Infrastructure
CIT Training | In Progress | User Services | Amelea | 3 | Pam, Suzanne, Tracy | yes |  | Librarians have skills to address patrons struggling with a crises. | Fostering Partnerships | Information Infrastructure
Volunteer program enhancements and administration | In Progress | User Services | TBD | [5 empty] | Partnerships
Grant management tool implementation | In Progress | User Services | Erin |  | John |  |  |  | Partnerships
Adaptive technologies implementation | In Progress | User Services | TBD | [5 empty] | Information Infrastructure
Economic development - Implement and evaluate contract with economic development liaison | Planning | User Services | Amelea | 2 | Tracy, Jim, Erin, Jessica | yes |  | Montanans have the skills they need to obtain jobs or open small businesses. Local economic development officials are aware of the value of libraries in economic development work. | Information Infrastructure
MTLibrary2Go - Conduct RFI/RFP | Planning | User Services | Cara |  |  | Yes |  |  | Information Infrastructure
OCLC (including MMP)- Conduct RFI/RFP | Planning | User Services | Cara |  | Chuck, Jennifer, Rebekah | Yes |  |  | Information Infrastructure
Realtime Network - create and grow Montana Network | Planning | User Services | Erin | [5 empty] | Partnerships | Info Infra?
Gigabit toolkit follow-up planning | Planning | User Services | Suzanne | 1 | Tracy, Jennie | maybe |  | Every Montanan has access to high speed Internet. | Information Infrastructure
Cost share formula analysis | Planning | User Services | Cara |  | TBD |  |  |  | Information Infrastructure
GeoEnabled Elections | Planning | User Services | Erin | [5 empty] | Partnerships
MMP Collections - unrepresented counties and under-represented counties | In Progress | User Services | Jennifer |  |  | Yes |  |  | Partnerships
Civic or civil engagement work | Planning | User Services | Amelea | 2 | Tracy, library staff
Public Library Board Member Development | Planning | User Services | Pam | 2 | Suzanne, Tracy | yes |  | Board members are enaged and active members in the library community in order to improve library services. | Information Infrastructure | Foster partnerships
Update website for librarians and board members | Planning | User Services | Pam | 1 | Tracy, Suzanne, Jo, Amelea | yes |  | Librarians and board members can find the resources they need to answer their questions. | Information Infrastructure
Foundations of librarianship course | Planning | User Services | Jo | 3 | Pam | yes |  | Librarians have the foundational knowledge needed to successfully run a library | Information Infrastructure
Virtual reality programming in libraries | Planning | User Services | Suzanne | 3 | Amelea | yes |  | Montanans have access to virtual reality programs to learn, connect, and play. | Information Infrastructure
Increase financial and community support for libraries | Planning | User Services | Tracy | 2 | Jennie | yes |  | Libraries have the community and financial support that allows them to offer services that help Montanans learn, make decisions, connect, and play.
Advisory Groups - improve engagement | Pre-planning | Admin
Agency Data & Records Management Strategy - including data sharing agreements | Pre-planning | Admin
Community Data Hub - What does this look like? What might we do with the hubs? | Pre-planning | Admin
Duplication on Demand for Talking Books | Pre-planning | Admin | [6 empty] | Partnerships
Information Infrastructure - Definition and gap analysis | Pre-planning | Admin | [6 empty] | Information Infrastructure
Outreach opportunities | Pre-planning | Admin | [6 empty] | Information Infrastructure
Partnerships - Define levels of engagement and ID partners; community charting; understanding partner needs | Pre-planning | Admin | [6 empty] | Information Infrastructure
Reporting - Identify and improve strategies for agencywide reporting | Pre-planning | Admin | [6 empty] | Information Infrastructure
Request Management - Integrated process and tool(s); internal and external requests | Pre-planning | Admin | [6 empty] | Partnerships
Audit MSL web applications and prioritize updates | Pre-planning | Info Products | Kenny |  | Stanley, Chuck, Bob, Tom, Joe |  |  |  | Information Infrastructure
Consistent public comment tool and process | Conceptual | Admin | [6 empty] | Partnerships
Productivity Tools - Password managers | Conceptual | Admin | [6 empty] | Funding
Productivity Tools - Tools updates and training | Conceptual | Admin | [6 empty] | Funding
Cross-training | Conceptual | Admin | [6 empty] | Information Infrastructure
Information Infrastructure
Information Infrastructure

## ESRI_MAPINFO_SHEET (hidden)
DO NOT EDIT
For Esri use only