## Project Tasks - Overview
Project ID | Project | Project Phase | Lead Work Group | Lead Staff | Additional Staff | Priority Rank From Lead | Start Date (estimate) | Target Completion Date | Project Status | Framework | Resources available | Intended Impact | Land Plan or LSTA Plan Goal | Notes | Group | Topic 1 | Topic 2 | Topic 3
1 | HB633 Study - Planning, Prep, Communication | In Progress | Administration | Jennie Stapp | MSL Commission, MSL Managers, MSL leads | 1 | 2019-07-01 | 2020-09-30 | On Schedule | Funding | Yes | Study will result in legislation that is passed by the 2021 Legislature that provides more diverse and stable funding for the State Library
2 | Study administration of the Montana Natural Heritage Program | In Progress | Administration | Jennie Stapp | Malissa Williams, Evan Hammer Bryce Maxell, MSL Commission | 2 | 2019-07-01 | 2020-12-11 | On Schedule | Funding | Yes | Staff will have more confidence that the administrative model of the MTNHP is appropriate and adequate; if changes are made they should improve work efficieny and financial stability for MTNHP and MSL |  |  | Natural Heritage Program
3 | Org Flattening | In Progress | Administration | Jennie Stapp | -- | 3 | 2019-07-01 | 2020-06-30 | On Schedule | Information Infrastructure | Yes
4 | IT upgrades | In Progress | Administration | Tom Marino | Kenny Ketner, Stanley Munson | 2 | 2019-07-01 | 2020-06-30 | Delayed | Information Infrastructure | Vendor Needed |  |  |  | Information Technology
5 | Performance management - Initiate use of state performance management system | Planning | Administration | Jennie Stapp | Malissa Williams, Evan Hammer, MSL Leads, all MSL staff | 4 |  | 2020-06-30 | Delayed | Funding | TBD | Staff and managers will have a dynamic performance management system to track staff progress on work objectives and overal performance; staff have confidence that they are performing their jobs satisfactorily.
6 | Pay equity and pay policy improvement | Planning | Administration | Malissa Williams | Jennie Stapp, Evan Hammer | 1 |  | 2020-06-30 | Not Started | Funding | TBD
7 | Intranet improvement | Planning | Administration | Malissa Williams | John Kilgour | 2 |  | 2020-06-30 | Not Started | Information Infrastructure | Yes |  |  |  | Information Technology
8 | Lidar - Implement Statewide Plan | In Progress | Information Management | Troy Blandford | Meghan Burns, Jeff Hedstom, GIS Tech(s), Erin Fashoway, Jessica Edwards, Bob Holliday, Kenny Ketner | 1 | 2019-07-01 | 2023-12-31 | On Schedule | Partnerships | Yes; funding for storage is ongoing | Statewide high-resolution elevation data by end of 2023, MSL becomes the repository for lidar data | Land Plan | End of 2023 is the ambitious goal for statewide lidar. Additional task completion dates are broken down in ProjectTaskDetails Sheet | GIS | LiDAR
9 | MARC record project | Planning | Information Management | Jim Kammerer | Jemma Hazen, Kenny Ketner | 1 |  | 2020-06-30 | On Schedule | Information Infrastructure | Contractor needed | Improved, cleaner access to print and digitized state publications. Supports growth of digital depositories among Montana libraries. | -- | Cataloging contractor has submitted sample deliverables and is asking additional questions. | Montana Shared Catalog | Cataloging
10 | Digital Public Library of America - Complete and evaluate ebook pilot | In Progress | Information Products | Jennie Stapp | Cara Orban, Kenny Ketner, Rebekah Kamp | 4 | 2019-07-01 | 2021-06-30 | On Schedule | Information Infrastructure |  |  |  |  | Statewide Projects | DPLA | Ebooks
11 | Productivity Tools - Project Management - identify tools, educate, and implement consistent practice | Complete | Information Products | Evan Hammer | Joe Tosoni, Tom Marino , Jennifer Birnel, Erin Fashoway, Jemma Hazen | 1 | 2019-07-01 | 2019-10-23 | On Schedule | Funding | Yes | Clear guidance for staff regarding tools available for project communication and task tracking. | -- | Following a staff team review of available tools (primarily Office 365 and Asana) it was determined that many productivity needs may be addressed through O365 while some more advance project management needs may justify Asana use. All staff were encouraged to use o365 where possible but ongoing Asana projects were allowed to continue and future projects may use Asana at the lead's discretion but ongoing/additional costs (beyond what has already been paid for in FY19) will come out of the lead program budget. | IT
12 | Montana Shared Catalog Cloud-based Integrated Library System reporting migration and data standardization (Phase 1) | In Progress | Information Products | Amy Marchwick | Jemma Hazen, Rebekah Kamp, Keiley McGregor | 2 | 2019-07-01 | 2020-06-30 | On Schedule | Information Infrastructure | Yes | We are making it possible to respond to user demand for more modern software. A cloud-based solution will be a more secure platform and increase support efficiences. Our vendor has made it clear that this is the direction they are moving, and to avoid being stuck on a legacy product, we are laying the foundation for a smooth transition. This is a first phase in laying the foundation for a cloud-based ILS in two to three years. |  | See project tracker online: https://app.asana.com/0/1126479711917387/1126479711917387 | Montana Shared Catalog
13 | Montana Shared Catalog security audit | Planning | Information Products | Amy Marchwick | Jemma Hazen, Rebekah Kamp, Tom Marino, Jennie Stapp | 1 |  | 2020-12-31 | On Schedule | Information Infrastructure | Startup funding in place for VPN; need to assess time | This project will bring us into compliance with state law for securing data in transit. |  | See project tracker online: https://app.asana.com/0/1126479711917387/1126479711917387 | Montana Shared Catalog
14 | Review of ArcGIS Server Environment Needs - Enterprise, Portal, EMCS Dev, etc. | In Progress | Information Products | Joe Tosoni | -- | 1 | 2019-07-01 | 2021-06-30 | Not Started | Information Infrastructure |  |  |  | IT | GIS | IT
15 | Cadastral Refresh - Interface updates and roll-out/promotion | In Progress | Information Products | Kenny Ketner | Erin Fashoway, John Kilgour, Amelea Kim | 1 | 2019-07-01 | 2020-04-13 | On Schedule | Information Infrastructure | N/A |  |  | User Services is helping to promote and document the new Cadastral interface | GIS | Cadastral
16 | Montana Shared Catalog mobile friendly ILS | In Progress | Information Products | Rebekah Kamp | Keiley McGregor, Amy Marchwick, Cara Orban | 1 | 2019-07-01 | 2020-06-30 | On Schedule | Information Infrastructure | Yes. If proceeding with an app, membership funding will be needed. | With 1/3 of Montana Shared Catalog users accessing the catalog via a mobile device, working to develop a mobile friendly ILS will increase access and improve user experience. | Collaboration, Information Access | We upgraded our online catalog development server in September. Testing is on schedule, and we anticipate upgrading production in March. The Montana Shared Catalog executive board received a mobile app demo from SirsiDynix. They requested more information on customization and an updated quote before the membership votes on the purchase. The vote will take place in advance of our spring membership meeting so we have adequate time to prepare the budget. | Montana Shared Catalog | LSTA | Collaboration | Information Access
17 | Montana Shared Catalog Standardize user sharing groups | Planning | Information Products | Amy Marchwick | Jemma Hazen, Rebekah Kamp, Cara Orban, Keiley McGregor | 4 |  | 2020-12-31 | On Schedule | Information Infrastructure | Yes; possible pilot funding | Increased standardization will position the MSC for a more competitive RFI/RFP process. A more standardized system is more sustainable and scalable and will increase support efficiences. It will make it easier to train member libraries because we will have uniform procedures based on uniform config. It will increase capacity for the courier, ultimately getting more books into the hands of Montanans and creating more equitable access. |  | See project tracker online: https://app.asana.com/0/1126479711917387/1126479711917387 | Montana Shared Catalog | LSTA | Collaboration | Information Access
18 | Census 2020 | In Progress | User Services | Jennie Stapp | Jo Flick, Tracy Cook | 5 | 2019-07-01 | 2020-06-30 | On Schedule | Partnerships | Yes | Ensure an accurate Census count in Montana | Community Leadership | User Services - completed 3 face-to-face trainings 1 webinar; developed print materials for libraries to share and display; produced webpage with links to resources; 19 libraries have signed up Census Champions | Continuing Education | Public libraries | Community Leadership | Adequate support
19 | Public Library Standards revision | In Progress | User Services | Tracy Cook | Jennie Stapp, Cara Orban | 4 | 2019-07-01 | 2020-06-30 | On Schedule | Information Infrastructure | Yes | Ensure that Montanans have access to library services sufficient unto their needs | Collaboration, Community Leadership, Adequate Support | Task force met; on second draft of standards to be shared with Commission at 2/2020 meeting | Consulting | Collaboration | Community Leadership
20 | Statewide data driven model/regional RIPL follow-up | In Progress | User Services | Tracy Cook | Jo Flick, Cara Orban, other MSL staff | 3 | 2019-07-01 | 2020-06-30 | On Schedule | Information Infrastructure | Yes | Attendees use data to plan and evaluate services. Attendees are better able to communicate the value of library services. | Adequate support | Regional RIPL completed; met with Colorado State Library staff; created draft plan for follow-up on RIPL; conducted evaluation and identified topics for follow-up training events | Continuing Education | RIPL | Public libraries
21 | Ready 2 Read Rendezvous | In Progress | User Services | Amelea Kim | Pam Henley, Jo Flick | 1 | 2019-07-01 | 2020-05-01 | On Schedule | Information Infrastructure | Yes | Librarians incorporate early literacy/early learning skill building in children's programming to assist Montana's youngest residents succeed later in life. | Community Leadership | Rendezvous held; completed initial evaluation; have projects from attendees; working on follow-up with attendees | Lifelong Learning |  | Community Leadership
22 | Transition to Bibliostat | In Progress | User Services | Pam Henley | Tracy Cook | 1 | 2019-07-01 | 2020-01-31 | On Schedule | Information Infrastructure | Yes | Create staff efficiences and provide librarians with access to statistics in order to evaluate their services and communicate their value. | Adequate support | Current data collection survey is in use, historical data still being developed | Consulting | Public libraries | Adequate support
23 | Implement strategic plan pathway continuing education model | In Progress | User Services | Jo Flick | Tracy Cook, Suzanne Reymer, Pam Henley | 5 | 2019-07-01 | 2020-04-10 | On Schedule | Information Infrastructure | Yes | Librarians have a certification pathway that assists them in achieving the library's strategic goals | Community Leadership | Pathway adopted; manual editing underway; MLA proposal accepted; working on forms within ASPeN; librarian testers recruited | Continuing Education |  | Community Leadership
24 | Directors Institute | In Progress | User Services | Jo Flick | Tracy Cook, Pam Henley, Suzanne Reymer, Cara Orban | 2 | 2019-07-01 | 2020-06-30 | On Schedule | Information Infrastructure | Yes | We build a cohort of collaborative leaders who trust each other, develop innovative ideas for libraries, are resilient, and able to have challenging conversations about barriers and scaling the project/program as needed. | Community Leadership | Facilitator, venue contracts completed; planning underway; | Continuing Education |  | Community Leadership
25 | Young Adult Services Librarian Association train the trainer conference attendance and Montana training | In Progress | User Services | Amelea Kim | Cody Allen (Billings Public Library), Heather Dickerson (Lewis & Clark Library) | 3 | 2019-07-01 | 2020-04-30 | On Schedule | Information Infrastructure | Yes | Librarians who serve young adults are empowered to provide relevant programming for their community members. | Community Leadership | 2 librarians attended national training; librarians and Kim created a plan for informing Montana librarians and training interested librarians on the topic | Lifelong Learning |  | Community Leadership
26 | Crisis Intervention Training at Federations | In Progress | User Services | Amelea Kim | Pam Henley, Suzanne Reymer, Tracy Cook | 3 | 2019-07-01 | 2020-05-30 | On Schedule | Partnerships | Yes | Librarians have skills to address patrons struggling with a crises. | Community Leadership | 2 Crisis Intervention Trainings at federation meetings held; will complete remainder in Spring; intial evaluation very positive - highlights training helped librarians identify signs of someone who may be consider suicide and provided ideas for helping de-escalate the situation | Lifelong Learning |  | Community Leadership
27 | Volunteer program enhancements and administration | In Progress | User Services | TBD | Erin Harris | 1 | 2019-07-01 | 2020-06-30 | Not Started | Partnerships | Yes |  |  |  | Talking Book Library
28 | Grant management tool implementation | In Progress | User Services | Erin Fashoway | John Kilgour | 1 | 2019-07-01 | 2020-12-31 | On Schedule | Partnerships |  |  |  |  | GIS
29 | Adaptive technologies implementation | In Progress | User Services | TBD | -- | 2 | 2019-07-01 | 2020-06-30 | Not Started | Information Infrastructure | Yes |  |  |  | Talking Book Library
30 | Economic development - Implement and evaluate contract with economic development liaison | In Progress | User Services | Amelea Kim | Tracy Cook, Jim Kammerer, Erin Fashoway, Jessica Edwards | 2 | 2019-07-01 | 2020-06-30 | On Schedule | Information Infrastructure | Yes | Montanans have the skills they need to obtain jobs or open small businesses. Local economic development officials are aware of the value of libraries in economic development work. | Community Leadership | Held initial planning meeting; working on limited solication details | Lifelong Learning | Community Leadership
31 | MTLibrary2Go - Conduct Request for Information/Request for Proposal | In Progress | User Services | Cara Orban | -- | 1 | 2019-07-01 | 2020-03-01 | On Schedule | Information Infrastructure | Yes | Every Montanan has access to popular downloadable and streaming e-content (ebooks and e-audiobooks, at minimum) because of a contract or contracts or interlibrary partnerships that create equitable, affordable access through all public libraries. | LSTA Goal 1: Collaboration |  | Statewide Projects | Ebooks | Collaboration
32 | Resource sharing contracts (including Montana Memory Project)- Conduct Request for Information/Request for Proposal | In Progress | User Services | Cara Orban | Chuck Vopicka, Jennifer Birnel, Rebekah Kamp | 1 | 2019-07-01 | 2020-03-01 | On Schedule | Information Infrastructure | Yes | People are able to discover and request the library materials they want, because of a contract that provides Montana library staff with the tools they need to facilitate interlibrary loan requests and to create or use high quality bibliographic records; people are able to discover Montana cultural heritage materials online through the MMP; taxpayers' dollars are optimally allocated to an appropriately scaled contract or contracts that meet libraries' needs in providing these services. | LSTA Goal 1: Collaboration |  | Statewide Projects | Resource sharing | Collaboration
33 | Realtime Network - create and grow Montana Network | Planning | User Services | Erin Fashoway | -- |  |  |  |  | Partnerships |  |  |  | Info Infra? | GIS | Realtime Network
34 | Gigabit toolkit follow-up planning | In Progress | User Services | Suzanne Reymer | Tracy Cook, Jennie Stapp | 1 | 2019-07-01 | 2020-06-30 | On Schedule | Information Infrastructure | maybe | Every Montanan has access to high speed Internet. | Internet access | Simmons college is analyzing the data to identify libraries that are most in need; staff will then evaluate to determine next steps; Reymer is reviewing Toolkit to plan for a training to help librarians interpret their report; Reymer reported on project at SHLB and is assisting Simmons with collecting comparison data from other states | Consulting | Public libraries | Internet Access
35 | Cost share formula revisions | Planning | User Services | Cara Orban | TBD | 2 |  | 2020-05-01 |  | Information Infrastructure |  |  |  |  | Statewide Projects | Resource sharing
36 | GeoEnabled Elections | Planning | User Services | Erin Fashoway | -- |  |  |  |  | Partnerships |  |  |  |  | GIS
37 | Montana Memory Project Collections - reduce the number of unrepresented counties and under-represented counties | In Progress | User Services | Jennifer Birnel | -- | 1 | 2019-07-01 | 2020-09-30 | On Schedule | Partnerships | Yes | Online access is created to documents currently restricted by the location of the content. | LSTA Goal 1: Collaboration | Visited Powell County (Grant-Kohrs Ranch) on 9/19/19 - In Progress: Submitted a Collection Application 9/25/19. Had several phone calls with Dawson County (Becky Gregg) prior to July 2, 2019 - In Progress: Submitted a Collection Application 5/10/19. Visited Toole County (Library) 8/13/19 - COMPLETE: Yeabooks added and completed 10/11/19. Long phone call with Carbon County (Dana) in early summer - In Progress: Submitted a Collection Application 10/3/19 | Montana Memory Project | Collaboration
38 | New Digital Archive for Montana Memory Project master files | In Progress | Information Products | Jennifer Birnel | Chuck Vopicka | 1 | 2019-07-01 | 2020-09-30 | On Schedule | Information Infrastructure | Yes - Montana Data Center | Preservation of MMP content supports continuation of collections and will make a platform change easier. | LSTA Goal 1: Collaboration | Working on getting copies of master files from contributors. Evaluating use of current Digital Archive with OCLC and making plans to end that relationship. Creating a Preservation Policy and flow chart of preservation work | Montana Memory Project | Collaboration
39 | Big Sky Country Digital Network Local webpage with Digital Public Library of America | In Progress | User Services | Jennifer Birnel | -- | 1 | 2019-07-01 | 2019-12-01 | On Schedule | Information Infrastructure | Yes | Online content from Big Sky Country Digital Network is easier to discover in a single platform | LSTA Goal 1: Collaboration | Waiting on 3rd iteration of the page. We are adding seperate tabs for Montana and North Dakota. The page is online at http://bscdn.dp.la/ | Montana Memory Project | Collaboration
40 | Civic or civil engagement work | In Progress | User Services | Amelea Kim | Tracy Cook, MSL staff | 2 | 2019-07-01 | 2020-05-30 | On Schedule | Partnerships |  | Community members work together to address community needs using the library space and library resources to make decisions and plan | Community Leadership | Small NAC subcommittee met decided to have law day working in conjunction with State Law Library; MSL staff will use what other libraries have done to create a framework and provide support for libraries interested in piloting the project | Lifelong Learning | Community Leadership
41 | Public Library Board Member Development | Planning | User Services | Pam Henley | Suzanne Reymer, Tracy Cook | 2 |  |  |  | Information Infrastructure | Yes | Board members are enaged and active members in the library community in order to improve library services. | #3 - Community Leadership | Foster partnerships | Consulting | Community Leadership
42 | Update website for librarians and board members | In Progress | User Services | Pam Henley | Tracy, Suzanne, Jo, Amelea | 1 | 2019-07-01 | 2020-03-01 | On Schedule | Information Infrastructure | Yes | Librarians and board members can find the resources they need to answer their questions. |  | Initial work updating the website has begun | Consulting
43 | Foundations of librarianship course | In Progress | User Services | Jo Flick | Pam Henley | 3 | 2019-07-01 | 2020-04-01 | On Schedule | Information Infrastructure | Yes | Librarians have the foundational knowledge needed to successfully run a library | Collaboration, Community Leadership, Adequate Support | Initial outline has been created | Continuing Education | Collaboration | Community Leadership | Adequate Support
44 | Virtual reality programming in libraries | Planning | User Services | Suzanne Reymer | Amelea Kim | 3 |  |  |  | Information Infrastructure | Yes | Montanans have access to virtual reality programs to learn, connect, and play. |  |  | Consulting | Lifelong Learning
45 | Increase financial and community support for libraries | In Progress | User Services | Tracy Cook | Jennie Stapp | 2 | 2019-07-01 | 2020-05-01 | On Schedule | Funding | Yes | Libraries have the community and financial support that allows them to offer services that help Montanans learn, make decisions, connect, and play. | Adequate Support | Collecting data from library directors and board members on training needs; MLA proposals have been accepted | Consulting | Adequate Support
46 | MSL Advisory Groups - improve efficiency and engagement | Pre-planning | Administration |  | -- |  |  |  |  | Partnerships
47 | Agency Data & Records Management Strategy - including data sharing agreements | Pre-planning | Administration |  | -- |  |  |  |  | Information Infrastructure
48 | Community Data Hub - What does this look like? What might we do with the hubs? | Pre-planning | Administration |  | -- |  |  |  |  | Information Infrastructure
49 | Duplication on Demand for Talking Books | Pre-planning | Administration |  | -- |  |  |  |  | Partnerships
50 | Information Infrastructure - Definition and gap analysis | Pre-planning | Administration |  | -- |  |  |  |  | Information Infrastructure
51 | Improved outreach opportunities and coordination | Pre-planning | Administration |  | -- |  |  |  |  | Information Infrastructure
52 | Partnerships - Define levels of engagement and ID partners; community charting; understanding partner needs | Pre-planning | Administration |  | -- |  |  |  |  | Information Infrastructure
53 | Reporting - Identify and improve strategies for agencywide reporting | In Progress | Information Products | Jessica Edwards | All MSL staff | 1 | 2019-09-01 | 2021-06-30 | On Schedule | Information Infrastructure | Yes | Develop more informative reporting that maximizes MSL's goals for a data drive managment model.
54 | Request Management - Integrated process and tool(s); internal and external requests | Pre-planning | Administration |  | -- |  |  |  |  | Partnerships
55 | Audit MSL web applications and prioritize updates | In Progress | Information Products | Kenny Ketner | Stanley Munson, Chuck Vopicka, Bob Holliday, Tom Marino, Joe Tosoni | 2 | 2019-07-01 | 2020-01-13 | On Schedule | Information Infrastructure | N/A | We have a priority list and detailed plans for upgrading our in-house web applications. |  | Now that our Information Products staff is back to normal numbers, we need to move forward in our daily work in an organized manner, rather than just putting out fires day to day.
56 | Consistent public comment tool and process | Conceptual | Administration |  | -- |  |  |  |  | Partnerships
57 | Productivity Tools - Password managers | Conceptual | Administration |  | -- |  |  |  |  | Funding
58 | Productivity Tools - Tools updates and training | Conceptual | Administration |  | -- |  |  |  |  | Funding
59 | Cross-training | Conceptual | Administration |  | -- |  |  |  |  | Information Infrastructure
60 | Migrate Montana Memory Project content from CONTENTdm to new platform | Conceptual | User Services | Jennifer Birnel | Chuck Vopicka |  |  |  |  | information Infrastructure |  | Provide a better platform for Montana Memory Project contributors and a better user interface to the end user |  | This project wil be necessary based on the outcome of the upcoming RFP

## Project Tasks - Milestones
Project ID | Project | Milestone | Milestone Start Date | Milestone Target Completion Date | Milestone Status | Project Phase | Lead Work Group | Lead Staff | Additional staff | Priority rank from Lead | Project Start Date | Project Target Completion Date | Project Status | Framework | Resources available | Intended Impact | Notes
1 | HB633 Study - Planning, Prep, Communication | 1. Review and provide comment on study scope | 2019-07-01 | 2019-08-16 | Completed | In Progress | Admin | Jennie | Commissioners, Managers and leads | 1 | 2019-07-01 | 2020-09-30 | On Schedule | Funding | Yes | Study will result in legislation that is passed by the 2021 Legislature that provides more diverse and stable funding for the State Library
1 |  | 2. Subcommittee meeting | 2019-09-01 | 2019-09-18 | Completed
1 |  | 3. Develop data and reporting based on Committee requests | 2019-09-18 | 2020-09-30 | On Schedule
1 |  | 4. Identify and recruit advocates | 2019-09-18 | 2020-09-30 | On Schedule
2 | Study administration of the Montana Natural Heritage Program | 1. Identify and organize study questions and resources to address questions | 2019-07-01 | 2019-09-30 | On Schedule | In Progress | Admin | Jennie | Malissa, Evan, Bryce, Commission | 2 | 2019-07-01 | 2020-12-11 | On Schedule | Funding | Yes | Staff will have more confidence that the administrative model of the MTNHP is appropriate and adequate; if changes are made they should improve work efficieny and financial stability for MTNHP and MSL
2 |  | 2. Communicate regularly with stakeholders (Commission, staff, UM , Budget Office) | 2019-07-01 | 2019-12-31 | On Schedule
2 |  | 3. Research study questions to determine whether or not adminstrative change is warranted | 2019-07-01 | 2019-12-11 | On Schedule
2 |  | 4. Make a final recommendation to the Commission regarding administrative changes | 2019-12-01 | 2019-12-11 | On Schedule
3 | Org Flattening | 1. Maintain ongoing communication with staff | 2019-07-01 | 2020-06-30 | On Schedule | In Progress | Admin | Jennie |  | 3 | 2019-07-01 | 2020-06-30 | On Schedule | Information Infrastructure
4 | IT upgrades | 1. Windows 10 | 2019-07-01 | 2020-01-14 | On Schedule | In Progress |  |  |  |  | 2019-07-01 | 2020-01-14 | On Schedule | Information Infrastructure | Yes
4 |  | 2. Server 2008 Migration | 2019-07-01 | 2021-06-30 | Delayed | [5 empty] | 2019-07-01 | 2021-06-30 | Delayed | Information Infrastructure | Staff time is limited | Migration is necessary because Microsoft Server 2008 R2 support ends
4 |  | 3. Virtual desktop implementation/Windows 10 | 2019-07-01 | 2020-06-30 | On Schedule |  | Admin | Tom | Joe, Stanley | 1 | 2019-07-01 | 2020-06-30 | On Schedule | Information Infrastructure | Yes
4 |  | 4. Website Updates - Reorganization/rewrite, Web Accessibility | 2019-07-01 | 2020-06-30 | Delayed |  | Admin | Tom | Kenny, Stanley | 2 | 2019-07-01 | 2020-06-30 | Delayed | Information Infrastructure | Vendor Needed |  | Will begin after VDI/Win 10
5 | Performance management - Initiate use of state performance management system | TBD | 2019-07-01 | 2020-06-30 | On Schedule | Planning | Admin | Jennie |  |  |  | 2020-06-30 | Delayed | Funding | TBD | Staff and managers will have a dynamic performance management system to track staff progress on work objectives and overal performance; staff have confidence that they are performing their jobs satisfactorily.
6 | Pay equity and pay policy improvement | TBD | 2019-07-01 | 2020-06-30 | On Schedule | Planning | Admin | Malissa | Jennie, Evan |  |  | 2020-06-30 | Not Started |  | TBD
7 | Intranet improvement | TBD | 2019-07-01 | 2020-06-30 | On Schedule | Planning | Admin | Malissa |  |  |  | 2020-06-30 | Not Started | Information Infrastructure | Yes
8 | Lidar - Implement Statewide Plan | 1. Develop posters/postcards one-pagers about State Lidar Plan | 2019-07-01 | 2019-09-20 | Delayed | In Progress | Info Management | Troy | Meghan Burns, Jeff Hedstom, GIS Tech(s), Erin Fashoway, Jessica Edwards, Bob Holliday, Kenny Ketner | 1 | 2019-07-01 | 2023-12-31 | On Schedule | Partnerships | Currently yes, though funding for storage and acquisition is ongoing | Statewide high-resolution elevation data by end of 2023, MSL becomes the repository for lidar data | original deadline was set for MACO conference; instead, Troy Blandford attended and presented at conference. User Services and Data Coordinator are needed to assist with outreach development
8 |  | 2. Apply for USGS 3D Elevation Program Broad Area Announcement in Fall 2019 for lidar acquisitions Spring/Fall 2020 | 2019-07-01 | 2019-11-08 | Completed | [8 empty] | Partnerships |  |  | Application was submitted to USGS Nov 8. Eight funding parnters were involved offering $928,547.62 in cost-share. Proposal to USGS is 24,285 square miles ($6,689,550). Award announcement anticipated Dec-Jan.
8 |  | 3. Gather, process, and store lidar data from all known acquisitions | 2019-11-08 | 2020-05-01 | On Schedule | [8 empty] | Information Infrastructure |  |  | Current inventory is 26 TB; projected to be 40 TB by end of FY20. Data processing is partially supported by NRCS funding
8 |  | 4. Develop prototype lidar data delivery system | 2020-05-01 | 2020-06-30 | On Schedule | [8 empty] | Information Infrastructure |  |  | Partially supported by NRCS funding
9 | MARC record project | Scope project. Develop contract. | 2019-07-01 | 2019-11-01 | Planning | Planning | Info Management | Jim Kammerer | Jemma Hazen, Kenny Ketner | 1 |  | 2020-06-30 | On Schedule | Information Infrastructure | Contractor needed | Improved, cleaner access to print and digitized state publications. Supports growth of digital depositories among Montana libraries. | Expect signed contract by 12/30/2019.
10 | Digital Public Library of America - Complete and evaluate ebook pilot | TBD | 2019-07-01 | 2021-06-30 | On Schedule | In Progress | Info Products | Jennie | Cara, Kenny, Rebekah |  | 2019-07-01 | 2021-06-30 | On Schedule | Information Infrastructure
11 | Productivity Tools - Project Management - identify tools, educate, and implement consistent practice | TBD | 2019-07-01 | 2019-10-23 | On Schedule | In Progress | Info Products | Evan | Joe, Tom, Jennifer, Erin, Jemma |  | 2019-07-01 | 2019-10-23 | Completed | Funding
12 | Montana Shared Catalog Cloud-based Integrated Library System reporting migration and data standardization (Phase 1) | 1. Audit five configuration areas and reports | 2019-07-01 | Dates dependent on lead assignment | On Schedule | In Progress | Info Products | MSC Lead | Amy, Jemma, Rebekah, Keiley | 2 | 2019-07-01 | 2020-06-30 | On Schedule | Information Infrastructure | Yes | We are making it possible to respond to user demand for more modern software. A cloud-based solution will be a more secure platform and increase support efficiences. Our vendor has made it clear that this is the direction they are moving, and to avoid being stuck on a legacy product, we are laying the foundation for a smooth transition. This is a first phase in laying the foundation for a cloud-based ILS in two to three years. | See project tracker online: https://app.asana.com/0/1126479711917387/1126479711917387
12 |  | 2. Establish standards and documentation |  |  | On Schedule
12 |  | 3. Migrate reports to BLUEcloud |  |  | On Schedule
12 |  | 4. BLUEcloud Central configuration with vendor |  |  | On Schedule
12 |  | 5. Develop and deliver training materials |  |  | On Schedule
13 | Montana Shared Catalog security audit | 1. Collect technology network information from member libraries | 2019-07-01 |  |  | Planning | Info Products | MSC Lead | Amy, Jemma, Rebekah, Tom, Jennie | 1 |  | 2020-12-31 | On Schedule | Information Infrastructure | Startup funding in place for VPN; need to assess time | This project will bring us into compliance with state law for securing data in transit. | See project tracker online: https://app.asana.com/0/1126479711917387/1126479711917387
13 |  | 2. Complete ITSD security audit form...Last step: Deploy VPN |  |  |  | Planning
14 | Review of ArcGIS Server Environment Needs - Enterprise, Portal, EMCS Dev, etc. | TBD | 2019-07-01 | 2021-06-30 | On Schedule | In Progress | Info Products | Joe |  |  | 2019-07-01 | 2021-06-30 | Not Started | Information Infrastructure |  |  | IT
15 | Cadastral Refresh - Interface updates and roll-out/promotion | TBD | 2019-07-01 | 2020-04-13 | On Schedule | In Progress | Info Products | Kenny |  |  | 2019-07-01 | 2020-04-13 | On Schedule | Information Infrastructure |  |  | User Services
16 | Montana Shared Catalog mobile friendly ILS | 1. Test server upgrade to enable responsive design | 2019-09-01 | 2019-09-30 | Completed | In Progress | Info Products | Rebekah Kamp | Keiley McGregor, Amy Marchwick, Cara Orban | 1 | 2019-07-01 | 2020-06-30 | On Schedule | Information Infrastructure | Yes. If proceeding with an app, membership funding will be needed. | LSTA Goal 1: Collaboration, Information Access. With 1/3 of Montana Shared Catalog users accessing the catalog via a mobile device, working to develop a mobile friendly ILS will increase access and improve user experience. | We upgraded our online catalog development server in September. Testing is on schedule, and we anticipate upgrading production in March. The Montana Shared Catalog executive board received a mobile app demo from SirsiDynix. They requested more information on customization and an updated quote before the membership votes on the purchase. The vote will take place in advance of our spring membership meeting so we have adequate time to prepare the budget.
16 |  | 2. Complete debugging, javascript widgets and CSS revisions | 2019-11-01 | 2019-12-31 | On Schedule
16 |  | 3. Mobile app put to membership vote | 2019-10-01 | 2019-10-31 | Delayed
16 |  | 4. Mobile profile testing | 2020-01-01 | 2020-02-28 | On Schedule
16 |  | 5. Update production | 2020-02-28 | 2020-03-31 | On Schedule
16 |  | 6. Document changes in knowledge base | 2020-03-31 | 2020-04-30 | On Schedule
17 | Montana Shared Catalog Standardize user sharing groups | 1. Establish a Sharing Group Committee with representation from all existing sharing groups and interested silo libraries. | 2019-10-01 | 2020-05-31 |  | Planning | Info Products | Amy | MSC Lead, Jemma, Rebekah, Cara, Keiley | 4 |  | 2020-12-31 | On Schedule | Information Infrastructure | Yes; possible pilot funding | Increased standardization will position the MSC for a more competitive RFI/RFP process. A more standardized system is more sustainable and scalable and will increase support efficiences. It will make it easier to train member libraries because we will have uniform procedures based on uniform config. It will increase capacity for the courier, ultimately getting more books into the hands of Montanans and creating more equitable access. | Dates dependent on lead assignment; Oct - solicit for committee volunteers; Jan - committee meeting; May - report on findings, See project tracker online: https://app.asana.com/0/1126479711917387/1126479711917387
18 | Census 2020 | 1. Printing of posters, etc; | 2019-07-01 | 2019-09-15 | Completed | In Progress | User Services | Jo Flick | Jennie, Tracy | 2 | 2019-07-01 | 2020-06-30 | On Schedule | Partnerships | yes | Ensure an accurate Census count in Montana | Info Mgmt/Info Infra?
18 |  | 2. Training | 2019-07-01 | 2019-09-30 | Completed
18 |  | 3. Census Week | 2020-04-01 | 2020-04-09 | On Schedule
18 |  | 4. Final Census Count Day | 2020-06-01 | 2020-06-30 | On Schedule
19 | Public Library Standards revision | 1. PLSTF Meeting | 2019-09-01 | 2019-09-13 | Completed | In Progress | User Services | Tracy Cook | Jennie, Cara | 4 | 2019-07-01 | 2020-06-30 | On Schedule | Information Infrastructure | yes | Ensure that Montanans have access to library services sufficient unto their needs | Funding?
19 |  | 2. 1st Draft of standards | 2019-09-13 | 2019-10-31 | Completed
19 |  | 3. Review and final draft of standards | 2019-10-31 | 2019-12-31 | On Schedule
19 |  | 4. Public comment | 2020-01-01 | 2020-02-28 | On Schedule
19 |  | 5. Administrative Rules process | 2020-02-28 | 2020-05-31 | On Schedule
19 |  | 6. Adoption of new standards | 2020-05-31 | 2020-06-30 | On Schedule
20 | Statewide data driven model/regional RIPL follow-up | 1. RIPL Training | 2019-10-06 | 2019-10-10 | Completed | In Progress | User Services | Jo Flick | Tracy Cook | 3 | 2019-07-01 | 2020-06-30 | On Schedule | Information Infrastructure | yes | Attendees use data to plan and evaluate services. Attendees are better able to communicate the value of library services. | Also could work towards secure sufficient funding
20 |  | 2. Follow-up meeting with Colorado State Library | 2019-10-10 | 2019-10-11 | Completed
20 |  | 3. Create follow-up plan | 2019-10-11 | 2019-11-30 | On Schedule
20 |  | 4. Implement follow-up plan | 2019-11-30 | 2020-05-31 | On Schedule
21 | Ready 2 Read Rendezvous | 1. R2R training offered | 2019-09-06 | 2019-09-08 | Completed | In Progress | User Services | Amelea | Pam, Jo | 1 | 2019-07-01 | 2020-05-01 | On Schedule | Information Infrastructure | yes | Librarians incorporate early literacy/early learning skill building in children's programming to assist Montana's youngest residents succeed later in life.
21 |  | 2. Follow-up with attendees | 2019-09-08 | 2020-01-31 | On Schedule
21 |  | 3. Application of what was learned | 2020-01-31 | 2020-05-31 | On Schedule
21 |  | 4. Evaluation of project | 2020-05-31 | 2020-08-30 | On Schedule
22 | Transition to Bibliostat | 1. Data is migrated to Bibliostat | 2019-07-01 | 2019-09-30 | Completed | In Progress | User Services | Pam | Tracy | 1 | 2019-07-01 | 2020-01-31 | On Schedule | Information Infrastructure | yes | Create staff efficiences and provide librarians with access to statistics in order to evaluate their services and communicate their value.
22 |  | 2. Statistics forms and historical reports are created | 2019-07-01 | 2019-09-30 | Completed
22 |  | 3. Product go live for libraries | 2019-07-01 | 2019-09-30 | Completed
22 |  | 4. Librarians submit statistics and can use historical reports | 2019-09-30 | 2019-11-30 | On Schedule
22 |  | 5. Statistics are successfully uploaded to IMLS | 2019-11-30 | 2020-02-02 | On Schedule
23 | Implement strategic plan pathway continuing education model | 1. Update certification manual with Commission adopted changes | 2019-07-01 | 2019-11-30 | On Schedule | In Progress | User Services | Jo Flick | Tracy, Suzanne, Pam | 5 | 2019-07-01 | 2020-04-10 | On Schedule | Information Infrastructure | yes | Librarians have a certification pathway that assists them in achieving the library's strategic goals
23 |  | 2. Webinar for librarians about new pathway | 2020-02-01 | 2020-02-28 | On Schedule
23 |  | 3. Assistance for librarians who follow the pathway | 2020-02-28 | 2020-03-30 | On Schedule
24 | Director's Institute | 1. Contract with facilitator is completed | 2019-07-01 | 2019-11-30 | Completed | In Progress | User Services | Jo Flick | Tracy, Pam, Suzanne, Cara | 2 | 2019-07-01 | 2020-06-30 | On Schedule | Information Infrastructure | yes | We build a cohort of collaborative leaders who trust each other, develop innovative ideas for libraries, are resilient, and able to have challenging conversations about barriers and scaling the project/program as needed. | Foster partnerships
24 |  | 2. Planning for workshop is completed | 2019-11-30 | 2020-01-31 | On Schedule
24 |  | 3. Institute is offered | 2020-06-01 | 2020-06-30 | On Schedule
24 |  | 4. Follow-up with attendees is completed | 2020-06-30 | 2020-09-30 | On Schedule
25 | Young Adult Services Librarian Association train the trainer conference attendance and Montana training | 1. Cody and Heather's attendance at YALSA train the trainer event | 2019-11-01 | 2019-11-30 | Completed | In Progress | User Services | Amelea | Cody Allen, Heather Dickerson | 3 | 2019-07-01 | 2019-04-30 | On Schedule | Information Infrastructure | yes | Librarians who serve young adults are empowered to provide relevant programming for their community members.
25 |  | 2. Offering of trainings for librarians | 2020-04-01 | 2020-04-09 | On Schedule | [10 empty] | Training planned for MLA 2020
26 | Crisis Intervention Training at Federations | 1. Fall training | 2019-09-01 | 2020-09-30 | Completed | In Progress | User Services | Amelea | Pam, Suzanne, Tracy | 3 | 2019-07-01 | 2020-05-30 | On Schedule | Fostering Partnerships | yes | Librarians have skills to address patrons struggling with a crises. | Information Infrastructure
26 |  | 2. Spring training | 2020-05-01 | 2020-05-31 | On Schedule
27 | Volunteer program enhancements and administration | TBD | 2019-07-01 | 2020-06-30 | On Schedule | In Progress | User Services | TBD |  |  | 2019-07-01 | 2020-06-30 | Not Started | Partnerships
28 | Grant management tool implementation | TBD | 2019-07-01 | 2020-06-30 | On Schedule | In Progress | User Services | Erin Fashoway | John Kilgour |  | 2019-07-01 | 2020-12-31 | On Schedule | Partnerships
29 | Adaptive technologies implementation | TBD | 2019-07-01 | 2020-06-30 | On Schedule | In Progress | User Services | TBD |  |  | 2019-07-01 | 2019-06-30 | Not Started | Information Infrastructure
30 | Economic development - Implement and evaluate contract with economic development liaison | 1. Creation of limited solicitation | 2019-07-01 | 2019-12-31 | On Schedule | Planning | User Services | Amelea | Tracy, Jim Kammerer, Erin, Jessica | 2 | 2019-07-01 | 2020-06-30 | On Schedule | Information Infrastructure | yes | Montanans have the skills they need to obtain jobs or open small businesses. Local economic development officials are aware of the value of libraries in economic development work.
30 |  | 2. Successful selection of vendor | 2019-12-31 | 2020-01-31 |  | Planning
30 |  | 3. Execution of contract | 2020-01-31 | 2020-05-31 |  | Planning
30 |  | 4. Deliverables that libraries can use | 2020-05-31 | 2020-08-30 |  | Planning
31 | MTLibrary2Go - Conduct Request for Information/Request for Proposal | 1. RFI release by | 2019-07-01 | 2019-09-15 |  | Planning | User Services | Cara |  |  | 2019-07-01 | 2020-03-01 | On Schedule | Information Infrastructure | Yes
31 |  | 2. RFI scoring | 2019-09-15 | 2019-10-31 |  | Planning
31 |  | 3. RFP release | 2019-10-31 | 2019-11-30 |  | Planning
31 |  | 4. RFP scoring | 2019-11-30 | 2020-01-31 |  | Planning
31 |  | 5. New contract and budget | 2020-01-31 | 2020-06-30 |  | Planning
32 | Resource sharing contracts (including Montana Memory Project)- Conduct Request for Information/Request for Proposal | 1. RFI release by | 2019-07-01 | 2019-09-15 |  | Planning | User Services | Cara | Chuck, Jennifer, Rebekah |  | 2019-07-01 | 2020-03-01 | On Schedule | Information Infrastructure | Yes
32 |  | 2. RFI scoring | 2019-09-15 | 2019-10-31 |  | Planning
32 |  | 3. RFP release | 2019-10-31 | 2019-11-30 |  | Planning
32 |  | 4. RFP scoring | 2019-11-30 | 2020-01-31 |  | Planning
32 |  | 5. New contract and budget | 2020-01-31 | 2020-06-30 |  | Planning
33 | Realtime Network - create and grow Montana Network | TBD | 2019-07-01 |  |  | Planning | User Services | Erin Fashoway | [5 empty] | Partnerships |  |  | Info Infra?
34 | Gigabit toolkit follow-up planning | 1. Analysis of data | 2019-07-01 | 2019-12-31 | On Schedule | Planning | User Services | Suzanne | Tracy, Jennie | 1 | 2019-07-01 | 2020-06-30 | On Schedule | Information Infrastructure | maybe | Every Montanan has access to high speed Internet.
34 |  | 2. Tell library story about data | 2019-12-31 | 2020-01-31 |  | Planning
34 |  | 3. Action plan on addressing deficiencies with hardware and Internet speeds | 2020-01-31 | 2020-02-28 |  | Planning
34 |  | 4. Obtain resources for addressing deficiencie | 2020-02-28 | 2020-06-30 |  | Planning
34 |  | 5. Assist libraries with addressing deficiencies. | 2020-02-28 | 2020-06-30 |  | Planning
35 | Cost share formula revisions | TBD | 2019-07-01 | 2020-06-30 |  | Planning | User Services | Cara | TBD |  |  | 2020-05-01 |  | Information Infrastructure
36 | GeoEnabled Elections | TBD | 2019-07-01 | 2020-06-30 |  | Planning | User Services | Erin Fashoway | [5 empty] | Partnerships
37 | Montana Memory Project Collections - reduce the number of unrepresented counties and under-represented counties | Collection from remaing 15 counties , improved collections from counties with only yearbooks | 2019-07-01 | 2020-06-01 | On Schedule | In Progress | User Services | Jennifer |  |  | 2019-07-01 | 2020-09-30 | On Schedule | Partnerships | Yes
38 | New Digital Archive for Montana Memory Project master files | TBD | 2019-07-01 | 2020-09-30 |  | In Progress |  |  |  |  | 2019-07-01 | 2020-09-30 | On Schedule
39 | Big Sky Country Digital Network Local webpage with Digital Public Library of America | TBD | 2019-07-01 | 2019-12-01 |  | In Progress |  |  |  |  | 2019-07-01 | 2019-12-01 | On Schedule
40 | Civic or civil engagement work | 1. Meeting of NAC sub-group and staff to identify a path | 2019-11-01 | 2019-11-30 | Completed | In Progress | User Services | Amelea | Tracy, library staff | 2 | 2019-07-01 | 2020-05-30 | On Schedule
40 |  | 2. Create an action plan for implementing the path | 2019-11-30 | 2019-12-31 | On Schedule
40 |  | 3. Deliverables from the plan are created | 2019-12-31 | 2020-05-31
40 |  | 4. Libraries use the deliverables | 2020-05-31 | 2020-06-30
41 | Public Library Board Member Development | 1. Increase number of trustees in MLA trustee interest group | 2019-07-01 | 2019-11-30 | On Schedule | In Progress | User Services | Pam | Suzanne, Tracy | 2 |  |  |  | Information Infrastructure | yes | Board members are enaged and active members in the library community in order to improve library services. | Foster partnerships
41 |  | 2. Increase enagement of the group | 2019-07-01 | 2019-11-30 | On Schedule
41 |  | 3. Offer trustee workshop | 2020-05-01 | 2020-05-31
41 |  | 4. Follow-up with attendees to see if learning was applied | 2020-06-01 | 2020-06-30
42 | Update website for librarians and board members | 1. Resources are updated | 2019-07-01 | 2019-12-31 | On Schedule | Planning | User Services | Pam | Tracy, Suzanne, Jo, Amelea | 1 | 2019-07-01 | 2020-03-01 | On Schedule | Information Infrastructure | yes | Librarians and board members can find the resources they need to answer their questions.
42 |  | 2. Website is made as user friendly as possible within existing parameters | 2019-07-01 | 2019-12-31 |  | Planning
42 |  | 3. End user feedback is obtained and acted upon if changes are needed | 2019-12-31 | 2020-05-31 |  | Planning
43 | Foundations of librarianship course | 1. Creation of modules for librarian course | 2019-07-01 | 2019-12-31 | On Schedule | Planning | User Services | Jo Flick | Pam | 3 | 2019-07-01 | 2020-04-01 | On Schedule | Information Infrastructure | yes | Librarians have the foundational knowledge needed to successfully run a library
44 | Virtual reality programming in libraries | 1. Research on implementation of VR in libraries | 2019-07-01 | 2019-12-31 | On Schedule | Planning | User Services | Suzanne | Amelea | 3 |  |  |  | Information Infrastructure | yes | Montanans have access to virtual reality programs to learn, connect, and play.
44 |  | 2. Create action plan for program | 2019-07-01 | 2019-12-31 |  | Planning
44 |  | 3. Offer session at OFFLINE | 2020-02-01 | 2020-02-28 |  | Planning
44 |  | 4. Deploy VR sets to Montana libraries | 2020-02-28 | 2020-05-31 |  | Planning
45 | Increase financial and community support for libraries | 1. Finalize the audience and plan for achieving this outcome | 2019-07-01 | 2019-11-30 | On Schedule | Planning | User Services | Tracy | Jennie | 2 | 2019-07-01 | 2019-05-01 |  |  | yes | Libraries have the community and financial support that allows them to offer services that help Montanans learn, make decisions, connect, and play.
45 |  | 2. Present a workshop for the audience | 2020-05-01 | 2020-05-31 |  | Planning
45 |  | 3. Follow-up with attendees | 2020-05-01 | 2020-05-31 |  | Planning
45 |  | 4. Evaluate progress and use to create the next plan and set of milestones | 2020-05-31 | 2020-06-30 |  | Planning
46 | MSL Advisory Groups - improve efficiency and engagement | TBD |  |  |  | Pre-planning | Admin
47 | Agency Data & Records Management Strategy - including data sharing agreements | TBD |  |  |  | Pre-planning | Admin
48 | Community Data Hub - What does this look like? What might we do with the hubs? | TBD |  |  |  | Pre-planning | Admin
49 | Duplication on Demand for Talking Books | TBD |  |  |  | Pre-planning | Admin | [6 empty] | Partnerships
50 | Information Infrastructure - Definition and gap analysis | TBD |  |  |  | Pre-planning | Admin | [6 empty] | Information Infrastructure
51 | Improved outreach opportunities and coordination | TBD |  |  |  | Pre-planning | Admin | [6 empty] | Information Infrastructure
52 | Partnerships - Define levels of engagement and ID partners; community charting; understanding partner needs | TBD |  |  |  | Pre-planning | Admin | Jennie | Commission, Jo, all staff |  |  |  |  | Information Infrastructure | Yes
53 | Reporting - Identify and improve strategies for agencywide reporting | TBD | 2019-09-01 | 2021-06-30 | On Schedule | In Progress | Admin | Jessica |  |  | 2019-09-01 | 2021-06-30 | On Schedule | Information Infrastructure
54 | Request Management - Integrated process and tool(s); internal and external requests | TBD |  |  |  | Pre-planning | Admin | [6 empty] | Partnerships
55 | Audit MSL web applications and prioritize updates | TBD | 2019-07-01 | 2020-01-13 | Delayed | In Progress | Info Products | Kenny | Stanley, Chuck, Bob, Tom, Joe |  | 2019-07-01 | 2020-01-13 | On Schedule | Information Infrastructure
56 | Consistent public comment tool and process | TBD |  |  |  | Conceptual | Admin | [6 empty] | Partnerships
57 | Productivity Tools - Password managers | TBD |  |  |  | Conceptual | Admin | [6 empty] | Funding
58 | Productivity Tools - Tools updates and training | TBD |  |  |  | Conceptual | Admin | [6 empty] | Funding
59 | Cross-training | TBD |  |  | On Schedule | Conceptual | Admin | [6 empty] | Information Infrastructure
60 | Migrate Montana Memory Project content from CONTENTdm to new platform | TBD |  |  |  | Conceptual | [7 empty] | Information Infrastructure

## Milestones (Old) (hidden)
Project ID | Known Projects, Tasks, Activities, Needs | Known Milestones | Milestone Start Date | Milestone Target Completion Date | Milestone Status | Project Phase | Lead Work Group | Lead Staff | Additional staff | Priority rank from Lead | Resources available | Intended Impact | Framework | Notes
1 | HB633 Study - Planning, Prep, Communication | 1. Review and provide comment on study scope |  | 2019-08-16 | Complete | Planning | Admin | Jennie | Commissioners, Managers and leads | 1 | Yes | Study will result in legislation that is passed by the 2021 Legislature that provides more diverse and stable funding for the State Library | Funding
1 |  | 2. Subcommittee meeting |  | 2019-09-18
1 |  | 3. Develop data and reporting based on Committee requests |  | On-going through September2020 | On Schedule
1 |  | 4. Identify and recruit advocates |  | On-going through September2020
2 | Study administration of the Montana Natural Heritage Program | 1. Identify and organize study questions and resources to address questions |  | 2019-09-30 | On Schedule | In Progress | Admin | Jennie | Malissa, Evan, Bryce, Commission | 2 | Yes | Staff will have more confidence that the administrative model of the MTNHP is appropriate and adequate; if changes are made they should improve work efficieny and financial stability for MTNHP and MSL | Funding
2 |  | 2. Communicate regularly with stakeholders (Commission, staff, UM , Budget Office) |  | On-going through December 2020 | On Schedule
2 |  | 3. Research study questions to determine whether or not adminstrative change is warranted |  | 2019-12-11 | On Schedule
2 |  | 4. Make a final recommendation to the Commission regarding administrative changes |  | 2019-12-11 | On Schedule
3 | Org Flattening | 1. Maintain ongoing communication with staff |  | Ongoing |  | In Progress | Admin | Jennie |  | 3
4 | Website Updates - Reorganization/rewrite, Web Accessibility |  |  |  | Will begin after VDI/Win 10 | In Progress | Admin | Tom | Kenny, Stanley | 2 | Vendor Needed |  | Information Infrastructure
5 | Virtual desktop implementation/Windows 10 |  |  | November 2019 Completion | Ongoing | In Progress | Admin | Tom | Joe, Stanley | 1 | Yes |  | Information Infrastructure
6 | Windows 10
7 | Server 2008 Migration
8 | Performance management - Initiate use of state performance management system |  |  |  |  | Planning | Admin | Jennie |  |  |  |  | Funding
9 | Pay equity and pay policy improvement |  |  |  |  | Planning | Admin | Malissa | Jennie, Evan
10 | Intranet improvement |  |  |  |  | Planning | Admin | Malissa |  |  |  |  | Information Infrastructure
11 | Lidar - Implement Statewide Plan | 1. Develop posters/postcards one-pagers about State Lidar Plan |  | 20-Sept-2019 (soft, then ongoing); | Delayed | In Progress | Info Management | Troy | Meghan Burns, Jeff Hedstom, GIS Tech(s), Erin Fashoway, Jessica Edwards, Bob Holliday, Kenny Ketner | 1 | Currently yes, though funding for storage and acquisition is ongoing | Statewide high-resolution elevation data by end of 2023, MSL becomes the repository for lidar data | Partnerships | original deadline was set for MACO conference; instead, Troy Blandford attended and presented at conference. User Services and Data Coordinator are needed to assist with outreach development
11 |  | 2. Apply for USGS 3D Elevation Program Broad Area Announcement in Fall 2019 for lidar acquisitions Spring/Fall 2020 |  | 8-Nov-2019 (hard); | Completed | [7 empty] | Partnerships | Application was submitted to USGS Nov 8. Eight funding parnters were involved offering $928,547.62 in cost-share. Proposal to USGS is 24,285 square miles ($6,689,550). Award announcement anticipated Dec-Jan.
11 |  | 3. Gather, process, and store lidar data from all known acquisitions |  | 1-May-2020 (soft); then ongoing | On Schedule | [7 empty] | Information Infrastructure | Current inventory is 26 TB; projected to be 40 TB by end of FY20. Data processing is partially supported by NRCS funding
11 |  | 4. Develop prototype lidar data delivery system |  | 30-June-2020 (soft). | On Schedule | [7 empty] | Information Infrastructure | Partially supported by NRCS funding
12 | MARC record project. | Scope project. Develop contract. |  | 11/1/2019 (tentative) | Planning | Planning | Info Management | Jim Kammerer | Jemma Hazen, Kenny Ketner | 1 | Contractor needed | Improved, cleaner access to print and digitized state publications. Supports growth of digital depositories among Montana libraries. | Information Infrastructure | Expect signed contract by 12/30/2019.
13 | Digital Public Library of America - Complete and evaluate ebook pilot |  |  |  |  | In Progress | Info Products | Jennie | Cara, Kenny, Rebekah |  |  |  | Information Infrastructure
14 | Productivity Tools - Project Management - identify tools, educate, and implement consistent practice |  |  |  |  | In Progress | Info Products | Evan | Joe, Tom, Jennifer, Erin, Jemma |  |  |  | Funding
15 | Montana Shared Catalog Cloud-based Integrated Library System reporting migration and data standardization (Phase 1) | 1. Audit five configuration areas and reports |  | Dates dependent on lead assignment |  | In Progress | Info Products | MSC Lead | Amy, Jemma, Rebekah, Keiley | 2 | Yes | We are making it possible to respond to user demand for more modern software. A cloud-based solution will be a more secure platform and increase support efficiences. Our vendor has made it clear that this is the direction they are moving, and to avoid being stuck on a legacy product, we are laying the foundation for a smooth transition. This is a first phase in laying the foundation for a cloud-based ILS in two to three years. | Information Infrastructure | See project tracker online: https://app.asana.com/0/1126479711917387/1126479711917387
15 |  | 2. Establish standards and documentation
15 |  | 3. Migrate reports to BLUEcloud
15 |  | 4. BLUEcloud Central configuration with vendor
15 |  | 5. Develop and deliver training materials
16 | Montana Shared Catalog security audit | 1. Collect technology network information from member libraries |  | Dates dependent on lead assignment |  | Planning | Info Products | MSC Lead | Amy, Jemma, Rebekah, Tom, Jennie | 1 | Startup funding in place for VPN; need to assess time | This project will bring us into compliance with state law for securing data in transit. | Information Infrastructure | See project tracker online: https://app.asana.com/0/1126479711917387/1126479711917387
16 |  | 2. Complete ITSD security audit form...Last step: Deploy VPN
17 | Review of ArcGIS Server Environment Needs - Enterprise, Portal, EMCS Dev, etc. |  |  |  |  | In Progress | Info Products | Joe |  |  |  |  | Information Infrastructure | IT
18 | Cadastral Refresh - Interface updates and roll-out/promotion |  |  |  |  | In Progress | Info Products | Kenny |  |  |  |  | Information Infrastructure | User Services
19 | Montana Shared Catalog mobile friendly ILS | 1. Test server upgrade to enable responsive design |  | 1. Sept-Oct - test server upgrade; | Completed (9/30/19) | In Progress | Info Products | Rebekah Kamp | Keiley McGregor, Amy Marchwick, Cara Orban | 1 | Yes. If proceeding with an app, membership funding will be needed. | LSTA Goal 1: Collaboration, Information Access. With 1/3 of Montana Shared Catalog users accessing the catalog via a mobile device, working to develop a mobile friendly ILS will increase access and improve user experience. | Information Infrastructure | We upgraded our online catalog development server in September. Testing is on schedule, and we anticipate upgrading production in March. The Montana Shared Catalog executive board received a mobile app demo from SirsiDynix. They requested more information on customization and an updated quote before the membership votes on the purchase. The vote will take place in advance of our spring membership meeting so we have adequate time to prepare the budget.
19 |  | 2. Complete debugging, javascript widgets and CSS revisions |  | 2. Nov-Dec - test server debugging and code revisions; | On schedule
19 |  | 3. Mobile app put to membership vote |  | 3. Oct - mobile app member vote; | Delayed (see note)
19 |  | 4. Mobile profile testing |  | 4. Jan-Feb - Mobile profile testing; | On schedule
19 |  | 5. Update production |  | 5. Mar - production update; | On schedule
19 |  | 6. Document changes in knowledge base |  | 6. Apr - documentation | On schedule
20 | Montana Shared Catalog Standardize user sharing groups | 1. Establish a Sharing Group Committee with representation from all existing sharing groups and interested silo libraries. |  | Dates dependent on lead assignment; Oct - solicit for committee volunteers; Jan - committee meeting; May - report on findings |  | Planning | Info Products | Amy | MSC Lead, Jemma, Rebekah, Cara, Keiley | 4 | Yes; possible pilot funding | Increased standardization will position the MSC for a more competitive RFI/RFP process. A more standardized system is more sustainable and scalable and will increase support efficiences. It will make it easier to train member libraries because we will have uniform procedures based on uniform config. It will increase capacity for the courier, ultimately getting more books into the hands of Montanans and creating more equitable access. | Information Infrastructure | See project tracker online: https://app.asana.com/0/1126479711917387/1126479711917387
21 | Census 2020 | 1. Printing of posters, etc; |  | 1. Mid-September | Completed | In Progress | User Services | Jo Flick | Jennie, Tracy | 2 | yes | Ensure an accurate Census count in Montana | Partnerships | Info Mgmt/Info Infra?
21 |  | 2. Training |  | 2. End of September | Completed
21 |  | 3. Census Week |  | 3. April 9, 2020
21 |  | 4. Final Census Count Day |  | 4. June 2020
22 | Public Library Standards revision | 1. PLSTF Meeting |  | 1. September 13, 2019 | Completed | In Progress | User Services | Tracy Cook | Jennie, Cara | 4 | yes | Ensure that Montanans have access to library services sufficient unto their needs | Information Infrastructure | Funding?
22 |  | 2. 1st Draft of standards |  | 2. October 2019 | Completed
22 |  | 3. Review and final draft of standards |  | 3. December 2020 | In progress
22 |  | 4. Public comment |  | 4. January/February 2020
22 |  | 5. Administrative Rules process |  | 5. Spring 2020
22 |  | 6. Adoption of new standards |  | 6. June 2020
23 | Statewide data driven model/regional RIPL follow-up | 1. RIPL Training |  | 1. October 10, 2019 | Completed | In Progress | User Services | Jo Flick | Tracy Cook | 3 | yes | Attendees use data to plan and evaluate services. Attendees are better able to communicate the value of library services. | Information Infrastructure | Also could work towards secure sufficient funding
23 |  | 2. Follow-up meeting with Colorado State Library |  | 2. October 11, 2019 | Completed
23 |  | 3. Create follow-up plan |  | 3. Fall 2019 | In progress
23 |  | 4. Implement follow-up plan |  | 4. Spring 2020
24 | Ready 2 Read Rendezvous | 1. R2R training offered |  | 1. September 2019 | Completed | In Progress | User Services | Amelea | Pam, Jo | 1 | yes | Librarians incorporate early literacy/early learning skill building in children's programming to assist Montana's youngest residents succeed later in life. | Information Infrastructure
24 |  | 2. Follow-up with attendees |  | 2. Fall/Winter 2019/2020 | In progress
24 |  | 3. Application of what was learned |  | 3. Spring 2020 | In progress
24 |  | 4. Evaluation of project |  | 4. Summer 2020
25 | Transition to Bibliostat | 1. Data is migrated to Bibliostat |  | 1. August/September 2019 | Completed | In Progress | User Services | Pam | Tracy | 1 | yes | Create staff efficiences and provide librarians with access to statistics in order to evaluate their services and communicate their value. | Information Infrastructure
25 |  | 2. Statistics forms and historical reports are created |  | 2. September 2019 | Statistis form - completed; historical in progress
25 |  | 3. Product go live for libraries |  | 3. September 2019 | Completed
25 |  | 4. Librarians submit statistics and can use historical reports |  | 4. Fall 2019 | In progress
25 |  | 5. Statistics are successfully uploaded to IMLS |  | 5. Winter 2020
26 | Implement strategic plan pathway continuing education model | 1. Update certification manual with Commission adopted changes |  | 1. Late fall 2019 | In progress | In Progress | User Services | Jo Flick | Tracy, Suzanne, Pam | 5 | yes | Librarians have a certification pathway that assists them in achieving the library's strategic goals | Information Infrastructure
26 |  | 2. Webinar for librarians about new pathway |  | 2. Winter 2020
26 |  | 3. Assistance for librarians who follow the pathway |  | 3. Winter/Spring 2020
27 | Director's Institute | 1. Contract with facilitator is completed |  | 1. Fall 2019 | Completed | In Progress | User Services | Jo Flick | Tracy, Pam, Suzanne, Cara | 2 | yes | We build a cohort of collaborative leaders who trust each other, develop innovative ideas for libraries, are resilient, and able to have challenging conversations about barriers and scaling the project/program as needed. | Information Infrastructure | Foster partnerships
27 |  | 2. Planning for workshop is completed |  | 2. Fall/winter 2019 | In progress
27 |  | 3. Institute is offered |  | 3. Early summer 2020
27 |  | 4. Follow-up with attendees is completed |  | 4. Summer/Fall 2020
28 | Young Adult Services Librarian Association train the trainer conference attendance and Montana training | 1. Cody and Heather's attendance at YALSA train the trainer event |  | 1. Fall 2019 | Completed | In Progress | User Services | Amelea | Cody Allen, Heather Dickerson | 3 | yes | Librarians who serve young adults are empowered to provide relevant programming for their community members. | Information Infrastructure
|  | 2. Offering of trainings for librarians |  | 2. 2020, possibly into 2021 | In progress | [6 empty] | Training planned for MLA 2020
29 | Crisis Intervention Training at Federations | 1. Trainings are complete |  | 1. Fall 2019/Spring 2020 | Fall completed | In Progress | User Services | Amelea | Pam, Suzanne, Tracy | 3 | yes | Librarians have skills to address patrons struggling with a crises. | Fostering Partnerships | Information Infrastructure
30 | Volunteer program enhancements and administration |  |  |  |  | In Progress | User Services | TBD |  |  |  |  | Partnerships
31 | Grant management tool implementation |  |  |  |  | In Progress | User Services | Erin Fashoway | John Kilgour |  |  |  | Partnerships
32 | Adaptive technologies implementation |  |  |  |  | In Progress | User Services | TBD |  |  |  |  | Information Infrastructure
33 | Economic development - Implement and evaluate contract with economic development liaison | 1. Creation of limited solicitation |  | 1. Winter 2019 | In progress | Planning | User Services | Amelea | Tracy, Jim Kammerer, Erin, Jessica | 2 | yes | Montanans have the skills they need to obtain jobs or open small businesses. Local economic development officials are aware of the value of libraries in economic development work. | Information Infrastructure
|  | 2. Successful selection of vendor |  | 2. Winter 2019
|  | 3. Execution of contract |  | 3. Spring 2020
|  | 4. Deliverables that libraries can use |  | 4. Summer 2020
34 | MTLibrary2Go - Conduct Request for Information/Request for Proposal | 1. RFI release by |  | 1. Mid-September; |  | Planning | User Services | Cara |  |  | Yes |  | Information Infrastructure
|  | 2. RFI scoring |  | 2. Late October;
|  | 3. RFP release |  | 3. Late November;
|  | 4. RFP scoring |  | 4. Late January;
|  | 5. New contract and budget |  | 5. June 30, 2020
35 | Resource sharing contracts (including Montana Memory Project)- Conduct Request for Information/Request for Proposal | 1. RFI release by |  | 1. Mid-September; |  | Planning | User Services | Cara | Chuck, Jennifer, Rebekah |  | Yes |  | Information Infrastructure
|  | 2. RFI scoring |  | 2. Late October;
|  | 3. RFP release |  | 3. Late November;
|  | 4. RFP scoring |  | 4. Late January;
|  | 5. New contract and budget |  | 5. June 30, 2020
36 | Realtime Network - create and grow Montana Network |  |  |  |  | Planning | User Services | Erin Fashoway |  |  |  |  | Partnerships | Info Infra?
37 | Gigabit toolkit follow-up planning | 1. Analysis of data |  | 1. Fall 2019 | In progress | Planning | User Services | Suzanne | Tracy, Jennie | 1 | maybe | Every Montanan has access to high speed Internet. | Information Infrastructure
|  | 2. Tell library story about data |  | 2. Fall 2019
|  | 3. Action plan on addressing deficiencies with hardware and Internet speeds |  | 3. Winter 2020
|  | 4. Obtain resources for addressing deficiencie |  | TBD
|  | 5. Assist libraries with addressing deficiencies. |  | TBD
38 | Cost share formula revisions | TBD |  |  |  | Planning | User Services | Cara | TBD |  |  |  | Information Infrastructure
39 | GeoEnabled Elections |  |  |  |  | Planning | User Services | Erin Fashoway |  |  |  |  | Partnerships
40 | Montana Memory Project Collections - reduce the number of unrepresented counties and under-represented counties | Collection from remaing 15 counties , improved collections from counties with only yearbooks |  | 2020-06-01 |  | In Progress | User Services | Jennifer |  |  | Yes |  | Partnerships
41 | New Digital Archive for Montana Memory Project master files
42 | Big Sky Country Digital Network Local webpage with Digital Public Library of America
43 | Civic or civil engagement work | 1. Meeting of NAC sub-group and staff to identify a path |  | 1. November 2019 | Completed | Planning | User Services | Amelea | Tracy, library staff | 2
|  | 2. Create an action plan for implementing the path |  | 2. Winter 2019 | In progress
|  | 3. Deliverables from the plan are created |  | 3. Spring 2020
|  | 4. Libraries use the deliverables |  | 4. Spring/Summer 2020
44 | Public Library Board Member Development | 1. Increase number of trustees in MLA trustee interest group |  | 1. Fall 2019 | In progress | Planning | User Services | Pam | Suzanne, Tracy | 2 | yes | Board members are enaged and active members in the library community in order to improve library services. | Information Infrastructure | Foster partnerships
|  | 2. Increase enagement of the group |  | 2. Fall 2019 | In progress
|  | 3. Offer trustee workshop |  | 3. Spring 2020
|  | 4. Follow-up with attendees to see if learning was applied |  | 4. Spring/early summer 2020
45 | Update website for librarians and board members | 1. Resources are updated |  | 1. Winter 2019 | In progress | Planning | User Services | Pam | Tracy, Suzanne, Jo, Amelea | 1 | yes | Librarians and board members can find the resources they need to answer their questions. | Information Infrastructure
|  | 2. Website is made as user friendly as possible within existing parameters |  | 2. Winter 2019
|  | 3. End user feedback is obtained and acted upon if changes are needed |  | 3. Spring 2020
46 | Foundations of librarianship course | 1. Creation of modules for librarian course |  | 1. Winter 2019 | In progress | Planning | User Services | Jo Flick | Pam | 3 | yes | Librarians have the foundational knowledge needed to successfully run a library | Information Infrastructure
47 | Virtual reality programming in libraries | 1. Research on implementation of VR in libraries |  | 1. Fall/winter 2019 | In progress | Planning | User Services | Suzanne | Amelea | 3 | yes | Montanans have access to virtual reality programs to learn, connect, and play. | Information Infrastructure
|  | 2. Create action plan for program |  | 2. Winter 2019
|  | 3. Offer session at OFFLINE |  | 3. February 2020
|  | 4. Deploy VR sets to Montana libraries |  | 4. Spring 2020
48 | Increase financial and community support for libraries | 1. Finalize the audience and plan for achieving this outcome |  | 1. Fall 2019 | In progress | Planning | User Services | Tracy | Jennie | 2 | yes | Libraries have the community and financial support that allows them to offer services that help Montanans learn, make decisions, connect, and play.
|  | 2. Present a workshop for the audience |  | 2. Spring 2020
|  | 3. Follow-up with attendees |  | 3. Spring 2020
|  | 4. Evaluate progress and use to create the next plan and set of milestones |  | 4. Late spring/early summer 2020
49 | MSL Advisory Groups - improve efficiency and engagement |  |  |  |  | Pre-planning | Admin
50 | Agency Data & Records Management Strategy - including data sharing agreements |  |  |  |  | Pre-planning | Admin
51 | Community Data Hub - What does this look like? What might we do with the hubs? |  |  |  |  | Pre-planning | Admin
52 | Duplication on Demand for Talking Books |  |  |  |  | Pre-planning | Admin | [5 empty] | Partnerships
53 | Information Infrastructure - Definition and gap analysis |  |  |  |  | Pre-planning | Admin | [5 empty] | Information Infrastructure
54 | Improved outreach opportunities and coordination |  |  |  |  | Pre-planning | Admin | [5 empty] | Information Infrastructure
55 | Partnerships - Define levels of engagement and ID partners; community charting; understanding partner needs |  |  |  |  | Pre-planning | Admin | Jennie | Commission, Jo, all staff |  | Yes |  | Information Infrastructure
56 | Reporting - Identify and improve strategies for agencywide reporting |  |  |  |  | Pre-planning | Admin | [5 empty] | Information Infrastructure
57 | Request Management - Integrated process and tool(s); internal and external requests |  |  |  |  | Pre-planning | Admin | [5 empty] | Partnerships
58 | Audit MSL web applications and prioritize updates |  |  |  | Delayed | Pre-planning | Info Products | Kenny | Stanley, Chuck, Bob, Tom, Joe |  |  |  | Information Infrastructure
59 | Consistent public comment tool and process |  |  |  |  | Conceptual | Admin | [5 empty] | Partnerships
60 | Productivity Tools - Password managers |  |  |  |  | Conceptual | Admin | [5 empty] | Funding
61 | Productivity Tools - Tools updates and training |  |  |  |  | Conceptual | Admin | [5 empty] | Funding
62 | Cross-training |  |  |  | In Progress | Conceptual | Admin | [5 empty] | Information Infrastructure
63 | Migrate Montana Memory Project content from CONTENTdm to new platform | [11 empty] | Information Infrastructure
Information Infrastructure

## Instructions
Project ID | Known Projects, Tasks, Activities, Needs | Project Phase | Lead Work Group | Lead Staff | Additional Staff | Priority rank from Lead | Start Date | Target Completion Date | Status | Framework | Resources Available | Intended Impact | Land Plan or LSTA Plan Goal | Notes
Disregard, to be filled for dashboard purposes | Project title (no acronyms please) | Completed | Administration | First and Last Name | First and Last Name | 1 | Month/Day/Year | Month/Day/Year | Completed | Funding | Yes | 1-3 descriptive sentences about the impact of the projectd | If the project meets a Land Plan or LSTA Plan goal, list that goal here | Status notes or other information helpful to MSL staff and/or Commission
|  | Conceptual | Information Management |  |  | 2 | Estimate if needed | Estimate if needed | Delayed | Information Infrastructure | If not, list needed resources here
|  | Pre-planning | Information Products |  |  | 3 |  |  | Not Started | Partnerships | or TBD
|  | Planning | User Services |  |  | 4 |  |  | On Schedule
|  | In Progress |  |  |  | 5
6
7
8
9
10
Please rank individual projects by
priority as directed by Leads

## ESRI_MAPINFO_SHEET (hidden)
DO NOT EDIT
For Esri use only

## Milestones (hidden)
Project ID | Project | Milestone | Lead work group | Lead staff | Additional staff | Priority rank | Project phase | Milestone start date (estimate) | Milestone target completion date | Milestone status | Framework | Resources available | Intended impact | Notes | Target completion date_original
1 | HB633 Study - Planning, Prep, Communication | 1. Review and provide comment on study scope | Admin | Jennie | Commissioners, Managers and leads | 1 | Planning | 2019-07-01 | 2019-08-16 | Completed | Funding | Yes | Study will result in legislation that is passed by the 2021 Legislature that provides more diverse and stable funding for the State Library |  | 2019-08-16
1 | HB633 Study - Planning, Prep, Communication | 2. Subcommittee meeting | Admin | Jennie | Commissioners, Managers and leads | 1 |  | 2019-09-01 | 2019-09-18 | Completed |  |  |  |  | 2019-09-18
1 | HB633 Study - Planning, Prep, Communication | 3. Develop data and reporting based on Committee requests | Admin | Jennie | Commissioners, Managers and leads | 1 |  | 2019-09-18 | 2020-09-30 | On Schedule |  |  |  |  | On-going through September2020
1 | HB633 Study - Planning, Prep, Communication | 4. Identify and recruit advocates | Admin | Jennie | Commissioners, Managers and leads | 1 |  | 2019-09-18 | 2020-09-30 | On Schedule |  |  |  |  | On-going through September2020
2 | Study administration of the Montana Natural Heritage Program | 1. Identify and organize study questions and resources to address questions | Admin | Jennie | Malissa, Evan, Bryce, Commission | 2 | In Progress | 2019-07-01 | 2019-09-30 | On Schedule | Funding | Yes | Staff will have more confidence that the administrative model of the MTNHP is appropriate and adequate; if changes are made they should improve work efficieny and financial stability for MTNHP and MSL |  | 2019-09-30
2 | Study administration of the Montana Natural Heritage Program | 2. Communicate regularly with stakeholders (Commission, staff, UM , Budget Office) | Admin | Jennie | Malissa, Evan, Bryce, Commission | 2 |  | 2019-07-01 | 2019-12-31 | On Schedule |  |  |  |  | On-going through December 2020
2 | Study administration of the Montana Natural Heritage Program | 3. Research study questions to determine whether or not adminstrative change is warranted | Admin | Jennie | Malissa, Evan, Bryce, Commission | 2 |  | 2019-07-01 | 2019-12-11 | On Schedule |  |  |  |  | 2019-12-11
2 | Study administration of the Montana Natural Heritage Program | 4. Make a final recommendation to the Commission regarding administrative changes | Admin | Jennie | Malissa, Evan, Bryce, Commission | 2 |  | 2019-12-01 | 2019-12-11 | On Schedule |  |  |  |  | 2019-12-11
3 | Org Flattening | 1. Maintain ongoing communication with staff | Admin | Jennie |  | 3 | In Progress | 2019-07-01 | 2020-06-30 | On Schedule |  |  |  |  | Ongoing
4 | Website Updates - Reorganization/rewrite, Web Accessibility | TBD | Admin | Tom | Kenny, Stanley | 2 | In Progress | 2019-07-01 | 2020-06-30 | On Schedule | Information Infrastructure | Vendor Needed |  | Will begin after VDI/Win 10
5 | Virtual desktop implementation/Windows 10 | TBD | Admin | Tom | Joe, Stanley | 1 | In Progress | 2019-07-01 | 2019-11-30 | On Schedule | Information Infrastructure | Yes |  |  | November 2019 Completion
6 | Windows 10 | TBD | Admin | Tom |  | 1 | In Progress | 2019-07-01 | 2020-01-14 | On Schedule | Information Infrastructure
7 | Server 2008 Migration | TBD | Admin | Tom | Joe | 3 | In Progress | 2019-07-01 | 2021-06-30 | On Schedule | Information Infrastructure | Staff time is limited | Migration is necessary because Microsoft Server 2008 R2 support ends
8 | Performance management - Initiate use of state performance management system | TBD | Admin | Jennie |  |  | Planning | 2019-07-01 | 2020-06-30 | On Schedule | Funding
9 | Pay equity and pay policy improvement | TBD | Admin | Malissa | Jennie, Evan |  | Planning | 2019-07-01 | 2020-06-30 | On Schedule
10 | Intranet improvement | TBD | Admin | Malissa |  |  | Planning | 2019-07-01 | 2020-06-30 | On Schedule | Information Infrastructure
11 | Lidar - Implement Statewide Plan | 1. Develop posters/postcards one-pagers about State Lidar Plan | Info Management | Troy | Meghan Burns, Jeff Hedstom, GIS Tech(s), Erin Fashoway, Jessica Edwards, Bob Holliday, Kenny Ketner | 1 | In Progress | 2019-07-01 | 2019-09-20 | Delayed | Partnerships | Currently yes, though funding for storage and acquisition is ongoing | Statewide high-resolution elevation data by end of 2023, MSL becomes the repository for lidar data | original deadline was set for MACO conference; instead, Troy Blandford attended and presented at conference. User Services and Data Coordinator are needed to assist with outreach development | 1. 20-Sept-2019 (soft, then ongoing);
11 | Lidar - Implement Statewide Plan | 2. Apply for USGS 3D Elevation Program Broad Area Announcement in Fall 2019 for lidar acquisitions Spring/Fall 2020 | Info Management | Troy | Meghan Burns, Jeff Hedstom, GIS Tech(s), Erin Fashoway, Jessica Edwards, Bob Holliday, Kenny Ketner | 1 |  | 2019-07-01 | 2019-11-08 | Completed | Partnerships |  |  | Application was submitted to USGS Nov 8. Eight funding parnters were involved offering $928,547.62 in cost-share. Proposal to USGS is 24,285 square miles ($6,689,550). Award announcement anticipated Dec-Jan. | 2. 8-Nov-2019 (hard);
11 | Lidar - Implement Statewide Plan | 3. Gather, process, and store lidar data from all known acquisitions | Info Management | Troy | Meghan Burns, Jeff Hedstom, GIS Tech(s), Erin Fashoway, Jessica Edwards, Bob Holliday, Kenny Ketner | 1 |  | 2019-11-08 | 2020-05-01 | On Schedule | Information Infrastructure |  |  | Current inventory is 26 TB; projected to be 40 TB by end of FY20. Data processing is partially supported by NRCS funding | 3. 1-May-2020 (soft); then ongoing
11 | Lidar - Implement Statewide Plan | 4. Develop prototype lidar data delivery system | Info Management | Troy | Meghan Burns, Jeff Hedstom, GIS Tech(s), Erin Fashoway, Jessica Edwards, Bob Holliday, Kenny Ketner | 1 |  | 2020-05-01 | 2020-06-30 | On Schedule | Information Infrastructure |  |  | Partially supported by NRCS funding | 4. 30-June-2020 (soft).
12 | MARC record project | 1. Scope project and develop contract | Info Management | Jim Kammerer | Jemma Hazen, Kenny Ketner | 1 | Planning | 2019-07-01 | 2019-11-01 |  | Information Infrastructure | Contractor needed | Improved, cleaner access to print and digitized state publications. Supports growth of digital depositories among Montana libraries. | Expect signed contract by 12/30/2019. | 11/1/2019 (tentative)
13 | Digital Public Library of America | 1. Complete and evaluate ebook pilot | Info Products | Jennie | Cara, Kenny, Rebekah |  | In Progress | 2019-07-01 | 2020-06-30 | On Schedule | Information Infrastructure
14 | Productivity Tools - Project Management | 1. Identify tools, educate, and implement consistent practice | Info Products | Evan | Joe, Tom, Jennifer, Erin, Jemma |  | In Progress | 2019-07-01 | 2020-06-30 | On Schedule | Funding
15 | MSC Cloud-based ILS reporting migration and data standardization (Phase 1) | 1. Audit five configuration areas and reports | Info Products | MSC Lead | Amy, Jemma, Rebekah, Keiley | 2 | In Progress | 2019-07-01 |  | On Schedule | Information Infrastructure | Yes | We are making it possible to respond to user demand for more modern software. A cloud-based solution will be a more secure platform and increase support efficiences. Our vendor has made it clear that this is the direction they are moving, and to avoid being stuck on a legacy product, we are laying the foundation for a smooth transition. This is a first phase in laying the foundation for a cloud-based ILS in two to three years. | See project tracker online: https://app.asana.com/0/1126479711917387/1126479711917387 | Dates dependent on lead assignment
15 | MSC Cloud-based ILS reporting migration and data standardization (Phase 1) | 2. Establish standards and documentation |  |  |  | 2 |  |  |  | On Schedule
15 | MSC Cloud-based ILS reporting migration and data standardization (Phase 1) | 3. Migrate reports to BLUEcloud |  |  |  | 2 |  |  |  | On Schedule
15 | MSC Cloud-based ILS reporting migration and data standardization (Phase 1) | 4. BLUEcloud Central configuration with vendor |  |  |  | 2 |  |  |  | On Schedule
15 | MSC Cloud-based ILS reporting migration and data standardization (Phase 1) | 5. Develop and deliver training materials |  |  |  | 2 |  |  |  | On Schedule
16 | MSC security audit | 1. Collect technology network information from member libraries | Info Products | MSC Lead | Amy, Jemma, Rebekah, Tom, Jennie | 1 | Planning | 2019-07-01 |  | On Schedule | Information Infrastructure | Startup funding in place for VPN; need to assess time | This project will bring us into compliance with state law for securing data in transit. | See project tracker online: https://app.asana.com/0/1126479711917387/1126479711917387 | Dates dependent on lead assignment
16 | MSC security audit | 2. Complete ITSD security audit form...Last step: Deploy VPN |  |  |  | 1 |  |  |  | On Schedule
17 | Review of ArcGIS Server Environment Needs - Enterprise, Portal, EMCS Dev, etc. |  | Info Products | Joe |  |  | In Progress | 2019-07-01 |  | On Schedule | Information Infrastructure |  |  | IT
18 | Cadastral Refresh | 1. Interface updates and roll-out/promotion | Info Products | Kenny |  |  | In Progress | 2019-07-01 |  | On Schedule | Information Infrastructure |  |  | User Services
19 | Montana Shared Catalog mobile friendly ILS | 1. Test server upgrade to enable responsive design | Info Products | Rebekah Kamp | Keiley McGregor, Amy Marchwick, Cara Orban | 1 | In Progress | 2019-09-01 | 2019-09-30 | Completed | Information Infrastructure | Yes. If proceeding with an app, membership funding will be needed. | LSTA Goal 1: Collaboration, Information Access. With 1/3 of Montana Shared Catalog users accessing the catalog via a mobile device, working to develop a mobile friendly ILS will increase access and improve user experience. | We upgraded our online catalog development server in September. Testing is on schedule, and we anticipate upgrading production in March. The Montana Shared Catalog executive board received a mobile app demo from SirsiDynix. They requested more information on customization and an updated quote before the membership votes on the purchase. The vote will take place in advance of our spring membership meeting so we have adequate time to prepare the budget. | 1. Sept-Oct - test server upgrade;
19 | Montana Shared Catalog mobile friendly ILS | 2. Complete debugging, javascript widgets and CSS revisions |  |  |  | 1 |  | 2019-11-01 | 2019-12-31 | On Schedule |  |  |  |  | 2. Nov-Dec - test server debugging and code revisions;
19 | Montana Shared Catalog mobile friendly ILS | 3. Mobile app put to membership vote |  |  |  | 1 |  | 2019-10-01 | 2019-10-31 | Delayed |  |  |  |  | 3. Oct - mobile app member vote;
19 | Montana Shared Catalog mobile friendly ILS | 4. Mobile profile testing |  |  |  | 1 |  | 2020-01-01 | 2020-02-28 | On Schedule |  |  |  |  | 4. Jan-Feb - Mobile profile testing;
19 | Montana Shared Catalog mobile friendly ILS | 5. Update production |  |  |  | 1 |  | 2020-02-28 | 2020-03-31 | On Schedule |  |  |  |  | 5. Mar - production update;
19 | Montana Shared Catalog mobile friendly ILS | 6. Document changes in knowledge base |  |  |  | 1 |  | 2020-03-31 | 2020-04-30 | On Schedule |  |  |  |  | 6. Apr - documentation
20 | Standardize MSC user sharing groups | 1. Establish a Sharing Group Committee with representation from all existing sharing groups and interested silo libraries | Info Products | Amy | MSC Lead, Jemma, Rebekah, Cara, Keiley | 4 | Planning | 2019-10-01 | 2020-05-31 | On Schedule | Information Infrastructure | Yes; possible pilot funding | Increased standardization will position the MSC for a more competitive RFI/RFP process. A more standardized system is more sustainable and scalable and will increase support efficiences. It will make it easier to train member libraries because we will have uniform procedures based on uniform config. It will increase capacity for the courier, ultimately getting more books into the hands of Montanans and creating more equitable access. | See project tracker online: https://app.asana.com/0/1126479711917387/1126479711917387 | Dates dependent on lead assignment; Oct - solicit for committee volunteers; Jan - committee meeting; May - report on findings
21 | Census 2020 | 1. Printing of posters and other materials | User Services | Jo Flick | Jennie, Tracy | 2 | In Progress | 2019-07-01 | 2019-09-15 | Completed | Partnerships | yes | Ensure an accurate Census count in Montana | Info Mgmt/Info Infra? | 1. Mid-September
21 | Census 2020 | 2. Training |  |  |  | 2 |  | 2019-07-01 | 2019-09-30 | Completed |  |  |  |  | 2. End of September
21 | Census 2020 | 3. Census Week |  |  |  | 2 |  | 2020-04-01 | 2020-04-09 | On Schedule |  |  |  |  | 3. April 9, 2020
21 | Census 2020 | 4. Final Census Count Day |  |  |  | 2 |  | 2020-06-01 | 2020-06-30 | On Schedule |  |  |  |  | 4. June 2020
22 | Public Library Standards revision | 1. PLSTF Meeting | User Services | Tracy Cook | Jennie, Cara | 4 | In Progress | 2019-09-01 | 2019-09-13 | Completed | Information Infrastructure | yes | Ensure that Montanans have access to library services sufficient unto their needs | Funding? | 1. September 13, 2019
22 | Public Library Standards revision | 2. 1st Draft of standards |  |  |  | 4 |  | 2019-09-13 | 2019-10-31 | Completed |  |  |  |  | 2. October 2019
22 | Public Library Standards revision | 3. Review and final draft of standards |  |  |  | 4 |  | 2019-10-31 | 2019-12-31 | On Schedule |  |  |  |  | 3. December 2020
22 | Public Library Standards revision | 4. Public comment |  |  |  | 4 |  | 2020-01-01 | 2020-02-28 | On Schedule |  |  |  |  | 4. January/February 2020
22 | Public Library Standards revision | 5. Administrative Rules process |  |  |  | 4 |  | 2020-02-28 | 2020-05-31 | On Schedule |  |  |  |  | 5. Spring 2020
22 | Public Library Standards revision | 6. Adoption of new standards |  |  |  | 4 |  | 2020-05-31 | 2020-06-30 | On Schedule |  |  |  |  | 6. June 2020
23 | Statewide data driven model/regional RIPL follow-up | 1. RIPL Training | User Services | Jo Flick | Tracy Cook | 3 | In Progress | 2019-10-06 | 2019-10-10 | Completed | Information Infrastructure | yes | Attendees use data to plan and evaluate services. Attendees are better able to communicate the value of library services. | Also could work towards secure sufficient funding | 1. October 10, 2019
23 | Statewide data driven model/regional RIPL follow-up | 2. Follow-up meeting with Colorado State Library |  |  |  | 3 |  | 2019-10-10 | 2019-10-11 | Completed |  |  |  |  | 2. October 11, 2019
23 | Statewide data driven model/regional RIPL follow-up | 3. Create follow-up plan |  |  |  | 3 |  | 2019-10-11 | 2019-11-30 | On Schedule |  |  |  |  | 3. Fall 2019
23 | Statewide data driven model/regional RIPL follow-up | 4. Implement follow-up plan |  |  |  | 3 |  | 2019-11-30 | 2020-05-31 | On Schedule |  |  |  |  | 4. Spring 2020
24 | Ready 2 Read Rendezvous | 1. R2R training offered | User Services | Amelea | Pam, Jo | 1 | In Progress | 2019-09-06 | 2019-09-08 | Completed | Information Infrastructure | yes | Librarians incorporate early literacy/early learning skill building in children's programming to assist Montana's youngest residents succeed later in life. |  | 1. September 2019
24 | Ready 2 Read Rendezvous | 2. Follow-up with attendees |  |  |  | 1 |  | 2019-09-08 | 2020-01-31 | On Schedule |  |  |  |  | 2. Fall/Winter 2019/2020
24 | Ready 2 Read Rendezvous | 3. Application of what was learned |  |  |  | 1 |  | 2020-01-31 | 2020-05-31 | On Schedule |  |  |  |  | 3. Spring 2020
24 | Ready 2 Read Rendezvous | 4. Evaluation of project |  |  |  | 1 |  | 2020-05-31 | 2020-08-30 | On Schedule |  |  |  |  | 4. Summer 2020
25 | Transition to Bibliostat | 1. Data is migrated to Bibliostat | User Services | Pam | Tracy | 1 | In Progress | 2019-07-01 | 2019-09-30 | Completed | Information Infrastructure | yes | Create staff efficiences and provide librarians with access to statistics in order to evaluate their services and communicate their value. |  | 1. August/September 2019
25 | Transition to Bibliostat | 2. Statistics forms and historical reports are created |  |  |  | 1 |  | 2019-07-01 | 2019-09-30 | Completed |  |  |  |  | 2. September 2019
25 | Transition to Bibliostat | 3. Product go live for libraries |  |  |  | 1 |  | 2019-07-01 | 2019-09-30 | Completed |  |  |  |  | 3. September 2019
25 | Transition to Bibliostat | 4. Librarians submit statistics and can use historical reports |  |  |  | 1 |  | 2019-09-30 | 2019-11-30 | On Schedule |  |  |  |  | 4. Fall 2019
25 | Transition to Bibliostat | 5. Statistics are successfully uploaded to IMLS |  |  |  | 1 |  | 2019-11-30 | 2020-02-02 | On Schedule |  |  |  |  | 5. Winter 2020
26 | Implement strategic plan pathway | 1. Update certification manual with Commission adopted changes | User Services | Jo Flick | Tracy, Suzanne, Pam | 5 | In Progress | 2019-07-01 | 2019-11-30 | On Schedule | Information Infrastructure | yes | Librarians have a certification pathway that assists them in achieving the library's strategic goals |  | 1. Late fall 2019
26 | Implement strategic plan pathway | 2. Webinar for librarians about new pathway |  |  |  | 5 |  | 2020-02-01 | 2020-02-28 | On Schedule |  |  |  |  | 2. Winter 2020
26 | Implement strategic plan pathway | 3. Assistance for librarians who follow the pathway |  |  |  | 5 |  | 2020-02-28 | 2020-03-30 | On Schedule |  |  |  |  | 3. Winter/Spring 2020
27 | Director's Institute | 1. Contract with facilitator is completed | User Services | Jo Flick | Tracy, Pam, Suzanne, Cara | 2 | In Progress | 2019-07-01 | 2019-11-30 | Completed | Information Infrastructure | yes | We build a cohort of collaborative leaders who trust each other, develop innovative ideas for libraries, are resilient, and able to have challenging conversations about barriers and scaling the project/program as needed. | Foster partnerships | 1. Fall 2019
27 | Director's Institute | 2. Planning for workshop is completed |  |  |  | 2 |  | 2019-11-30 | 2020-01-31 | On Schedule |  |  |  |  | 2. Fall/winter 2019
27 | Director's Institute | 3. Institute is offered |  |  |  | 2 |  | 2020-06-01 | 2020-06-30 | On Schedule |  |  |  |  | 3. Early summer 2020
27 | Director's Institute | 4. Follow-up with attendees is completed |  |  |  | 2 |  | 2020-06-30 | 2020-09-30 | On Schedule |  |  |  |  | 4. Summer/Fall 2020
28 | YALSA Training | 1. Cody and Heather's attendance at YALSA train the trainer event | User Services | Amelea | Cody Allen, Heather Dickerson | 3 | In Progress | 2019-11-01 | 2019-11-30 | Completed | Information Infrastructure | yes | Librarians who serve young adults are empowered to provide relevant programming for their community members. |  | 1. Fall 2019
28 | YALSA Training | 2. Offering of trainings for librarians |  |  |  | 3 |  | 2020-04-01 | 2020-04-09 | On Schedule |  |  | Training planned for MLA 2020 |  | 2. 2020, possibly into 2021
29 | CIT Training | 1. Fall training | User Services | Amelea | Pam, Suzanne, Tracy | 3 | In Progress | 2019-09-01 | 2020-09-30 | Completed | Fostering Partnerships | yes | Librarians have skills to address patrons struggling with a crises. | Information Infrastructure | 1. Fall 2019/Spring 2020
29 | CIT Training | 2. Spring training | User Services | Amelea | Pam, Suzanne, Tracy | 3 | In Progress | 2020-05-01 | 2020-05-31 | On Schedule
30 | Volunteer program enhancements and administration | TBD | User Services | TBD |  |  | In Progress |  |  |  | Partnerships
31 | Grant management tool implementation | TBD | User Services | Erin Fashoway | John Kilgour |  | In Progress |  |  |  | Partnerships
32 | Adaptive technologies implementation | TBD | User Services | TBD |  |  | In Progress |  |  |  | Information Infrastructure
33 | Economic development - Implement and evaluate contract with economic development liaison | 1. Creation of limited solicitation | User Services | Amelea | Tracy, Jim Kammerer, Erin, Jessica | 2 | Planning | 2019-07-01 | 2019-12-31 | On Schedule | Information Infrastructure | yes | Montanans have the skills they need to obtain jobs or open small businesses. Local economic development officials are aware of the value of libraries in economic development work. |  | 1. Winter 2019
33 | Economic development - Implement and evaluate contract with economic development liaison | 2. Successful selection of vendor | User Services | Amelea | Tracy, Jim Kammerer, Erin, Jessica | 2 |  | 2019-12-31 | 2020-01-31 | On Schedule |  |  |  |  | 2. Winter 2019
33 | Economic development - Implement and evaluate contract with economic development liaison | 3. Execution of contract | User Services | Amelea | Tracy, Jim Kammerer, Erin, Jessica | 2 |  | 2020-01-31 | 2020-05-31 | On Schedule |  |  |  |  | 3. Spring 2020
33 | Economic development - Implement and evaluate contract with economic development liaison | 4. Deliverables that libraries can use | User Services | Amelea | Tracy, Jim Kammerer, Erin, Jessica | 2 |  | 2020-05-31 | 2020-08-30 | On Schedule |  |  |  |  | 4. Summer 2020
34 | MTLibrary2Go - Conduct RFI/RFP | 1. RFI release by | User Services | Cara |  |  | Planning | 2019-07-01 | 2019-09-15 |  | Information Infrastructure | Yes |  |  | 1. Mid-September;
34 | MTLibrary2Go - Conduct RFI/RFP | 2. RFI scoring | [5 empty] | 2019-09-15 | 2019-10-31 | [5 empty] | 2. Late October;
34 | MTLibrary2Go - Conduct RFI/RFP | 3. RFP release | [5 empty] | 2019-10-31 | 2019-11-30 | [5 empty] | 3. Late November;
34 | MTLibrary2Go - Conduct RFI/RFP | 4. RFP scoring | [5 empty] | 2019-11-30 | 2020-01-31 | [5 empty] | 4. Late January;
34 | MTLibrary2Go - Conduct RFI/RFP | 5. New contract and budget | [5 empty] | 2020-01-31 | 2020-06-30 | [5 empty] | 5. June 30, 2020
35 | OCLC (including MMP)- Conduct RFI/RFP | 1. RFI release by | User Services | Cara | Chuck, Jennifer, Rebekah |  | Planning | 2019-07-01 | 2019-09-15 |  | Information Infrastructure | Yes |  |  | 1. Mid-September;
35 | OCLC (including MMP)- Conduct RFI/RFP | 2. RFI scoring | [5 empty] | 2019-09-15 | 2019-10-31 | [5 empty] | 2. Late October;
35 | OCLC (including MMP)- Conduct RFI/RFP | 3. RFP release | [5 empty] | 2019-10-31 | 2019-11-30 | [5 empty] | 3. Late November;
35 | OCLC (including MMP)- Conduct RFI/RFP | 4. RFP scoring | [5 empty] | 2019-11-30 | 2020-01-31 | [5 empty] | 4. Late January;
35 | OCLC (including MMP)- Conduct RFI/RFP | 5. New contract and budget | [5 empty] | 2020-01-31 | 2020-06-30 | [5 empty] | 5. June 30, 2020
36 | Realtime Network - create and grow Montana Network | TBD | User Services | Erin Fashoway |  |  | Planning |  |  |  | Partnerships |  |  | Info Infra?
37 | Gigabit toolkit follow-up planning | 1. Analysis of data | User Services | Suzanne | Tracy, Jennie | 1 | Planning | 2019-07-01 | 2019-12-31 | On Schedule | Information Infrastructure | maybe | Every Montanan has access to high speed Internet. |  | 1. Fall 2019
37 | Gigabit toolkit follow-up planning | 2. Tell library story about data |  |  |  | 1 |  | 2019-12-31 | 2020-01-31 | On Schedule |  |  |  |  | 2. Fall 2019
37 | Gigabit toolkit follow-up planning | 3. Action plan on addressing deficiencies with hardware and Internet speeds |  |  |  | 1 |  | 2020-01-31 | 2020-02-28 | On Schedule |  |  |  |  | 3. Winter 2020
37 | Gigabit toolkit follow-up planning | 4. Obtain resources for addressing deficiencies |  |  |  | 1 |  | 2020-02-28 | 2020-06-30 | On Schedule |  |  |  |  | TBD
37 | Gigabit toolkit follow-up planning | 5. Assist libraries with addressing deficiencies |  |  |  | 1 |  | 2020-02-28 | 2020-06-30 | On Schedule |  |  |  |  | TBD
38 | Cost share formula analysis | TBD | User Services | Cara | TBD |  | Planning | 2019-07-01 | 2020-06-30 | On Schedule | Information Infrastructure
39 | GeoEnabled Elections | TBD | User Services | Erin Fashoway |  |  | Planning | 2019-07-01 | 2020-06-30 | On Schedule | Partnerships
40 | MMP Collections - unrepresented counties and under-represented counties | 1. Collection from remaing 15 counties , improved collections from counties with only yearbooks | User Services | Jennifer |  |  | In Progress | 2019-07-01 | 2020-06-30 | On Schedule | Partnerships | Yes |  |  | 2020-06-01
41 | New Digital Archive for Montana Memory Project master files | TBD | Info Products | Jennifer Birnel | Chuck Vopicka | 1 | In Progress | 2019-07-01 | 2020-09-30 | On Schedule | Information Infrastructure | Yes - Montana Data Center |  | Working on getting copies of master files from contributors. Evaluating use of current Digital Archive with OCLC and making plans to end that relationship. Creating a Preservation Policy and flow chart of preservation work | Preservation of MMP content supports continuation of collections and will make a platform change easier.
42 | Big Sky Country Digital Network Local webpage with Digital Public Library of America | TBD | User Services | Jennifer Birnel |  | 1 | In Progress | 2019-07-01 | 2019-12-01 | On Schedule | Information Infrastructure | Yes |  | Waiting on 3rd iteration of the page. We are adding seperate tabs for Montana and North Dakota. The page is online at http://bscdn.dp.la/ | Online content from Big Sky Country Digital Network is easier to discover in a single platform
43 | Civic or civil engagement work | 1. Meeting of NAC sub-group and staff to identify a path | User Services | Amelea | Tracy, library staff | 2 | Planning | 2019-11-01 | 2019-11-30 | Completed |  |  |  |  | 1. November 2019
43 | Civic or civil engagement work | 2. Create an action plan for implementing the path |  |  |  | 2 |  | 2019-11-30 | 2019-12-31 | On Schedule |  |  |  |  | 2. Winter 2019
43 | Civic or civil engagement work | 3. Deliverables from the plan are created |  |  |  | 2 |  | 2019-12-31 | 2020-05-31 | On Schedule |  |  |  |  | 3. Spring 2020
43 | Civic or civil engagement work | 4. Libraries use the deliverables |  |  |  | 2 |  | 2020-05-31 | 2020-06-30 | On Schedule |  |  |  |  | 4. Spring/Summer 2020
44 | Public Library Board Member Development | 1. Increase number of trustees in MLA trustee interest group | User Services | Pam | Suzanne, Tracy | 2 | Planning | 2019-07-01 | 2019-11-30 | On Schedule | Information Infrastructure | yes | Board members are enaged and active members in the library community in order to improve library services. | Foster partnerships | 1. Fall 2019
44 | Public Library Board Member Development | 2. Increase enagement of the group |  |  |  | 2 |  | 2019-07-01 | 2019-11-30 | On Schedule |  |  |  |  | 2. Fall 2019
44 | Public Library Board Member Development | 3. Offer trustee workshop |  |  |  | 2 |  | 2020-05-01 | 2020-05-31 | On Schedule |  |  |  |  | 3. Spring 2020
44 | Public Library Board Member Development | 4. Follow-up with attendees to see if learning was applied |  |  |  | 2 |  | 2020-06-01 | 2020-06-30 | On Schedule |  |  |  |  | 4. Spring/early summer 2020
45 | Update website for librarians and board members | 1. Resources are updated | User Services | Pam | Tracy, Suzanne, Jo, Amelea | 1 | Planning | 2019-07-01 | 2019-12-31 | On Schedule | Information Infrastructure | yes | Librarians and board members can find the resources they need to answer their questions. |  | 1. Winter 2019
45 | Update website for librarians and board members | 2. Website is made as user friendly as possible within existing parameters |  |  |  | 1 |  | 2019-07-01 | 2019-12-31 | On Schedule |  |  |  |  | 2. Winter 2019
45 | Update website for librarians and board members | 3. End user feedback is obtained and acted upon if changes are needed |  |  |  | 1 |  | 2019-12-31 | 2020-05-31 | On Schedule |  |  |  |  | 3. Spring 2020
46 | Foundations of librarianship course | 1. Creation of modules for librarian course | User Services | Jo Flick | Pam | 3 | Planning | 2019-07-01 | 2019-12-31 | On Schedule | Information Infrastructure | yes | Librarians have the foundational knowledge needed to successfully run a library |  | 1. Winter 2019
47 | Virtual reality programming in libraries | 1. Research on implementation of VR in libraries | User Services | Suzanne | Amelea | 3 | Planning | 2019-07-01 | 2019-12-31 | On Schedule | Information Infrastructure | yes | Montanans have access to virtual reality programs to learn, connect, and play. |  | 1. Fall/winter 2019
47 | Virtual reality programming in libraries | 2. Create action plan for program |  |  |  | 3 |  | 2019-07-01 | 2019-12-31 | On Schedule |  |  |  |  | 2. Winter 2019
47 | Virtual reality programming in libraries | 3. Offer session at OFFLINE |  |  |  | 3 |  | 2020-02-01 | 2020-02-28 | On Schedule |  |  |  |  | 3. February 2020
47 | Virtual reality programming in libraries | 4. Deploy VR sets to Montana libraries |  |  |  | 3 |  | 2020-02-28 | 2020-05-31 | On Schedule |  |  |  |  | 4. Spring 2020
48 | Increase financial and community support for libraries | 1. Finalize the audience and plan for achieving this outcome | User Services | Tracy | Jennie | 2 | Planning | 2019-07-01 | 2019-11-30 | On Schedule |  | yes | Libraries have the community and financial support that allows them to offer services that help Montanans learn, make decisions, connect, and play. |  | 1. Fall 2019
48 | Increase financial and community support for libraries | 2. Present a workshop for the audience |  |  |  | 2 |  | 2020-05-01 | 2020-05-31 | On Schedule |  |  |  |  | 2. Spring 2020
48 | Increase financial and community support for libraries | 3. Follow-up with attendees |  |  |  | 2 |  | 2020-05-01 | 2020-05-31 | On Schedule |  |  |  |  | 3. Spring 2020
48 | Increase financial and community support for libraries | 4. Evaluate progress and use to create the next plan and set of milestones |  |  |  | 2 |  | 2020-05-31 | 2020-06-30 | On Schedule |  |  |  |  | 4. Late spring/early summer 2020
49 | Advisory Groups - improve engagement | TBD | Admin |  |  |  | Pre-planning
50 | Agency Data & Records Management Strategy - including data sharing agreements | TBD | Admin |  |  |  | Pre-planning
51 | Community Data Hub - What does this look like? What might we do with the hubs? (e.g. County level, geographically referenced government information and search interface to return all available info.) | TBD | Admin |  |  |  | Pre-planning
52 | Duplication on Demand for Talking Books | TBD | Admin |  |  |  | Pre-planning |  |  |  | Partnerships
53 | Information Infrastructure - Definition and gap analysis | TBD | Admin |  |  |  | Pre-planning |  |  |  | Information Infrastructure
54 | Outreach opportunities | TBD | Admin |  |  |  | Pre-planning |  |  |  | Information Infrastructure
55 | Partnerships - Define levels of engagement and ID partners; community charting; understanding partner needs | TBD | Admin | Jennie | Commission, Jo, all staff |  | Pre-planning |  |  |  | Information Infrastructure | Yes
56 | Reporting - Identify and improve strategies for agencywide reporting | TBD | Admin |  |  |  | Pre-planning |  |  |  | Information Infrastructure
57 | Request Management - Integrated process and tool(s); internal and external requests | TBD | Admin |  |  |  | Pre-planning |  |  |  | Partnerships
59 | Consistent public comment tool and process | TBD | Admin |  |  |  | Conceptual |  |  |  | Partnerships
60 | Productivity Tools - Password managers | TBD | Admin |  |  |  | Conceptual |  |  |  | Funding
61 | Productivity Tools - Tools updates and training | TBD | Admin |  |  |  | Conceptual |  |  |  | Funding
62 | Cross-training | TBD | Admin |  |  |  | Conceptual |  |  | On Schedule | Information Infrastructure
58 | Audit MSL web applications and prioritize updates | TBD | Info Products | Kenny | Stanley, Chuck, Bob, Tom, Joe |  | Pre-planning |  |  | Delayed | Information Infrastructure
63 | Migrate Montana Memory Project content from CONTENTdm to new platform | TBD | User Services | Jennifer Birnel | Chuck Vopicka |  | Conceptual |  |  |  | information Infrastructure |  |  | This project wil be necessary based on the outcome of the upcoming RFP | Provide a better platform for Montana Memory Project contributors and a better user interface to the end user
Information Infrastructure